## Issue Navigator
Key | Summary | Status | Resolution | Created | Start Date | End Date | Change Author | Change Time | Changed Field | Old value | New Value
B4B-56 | First mockup | To Do |  | 2012-07-21 13:52 | 2012-05-10 | 2012-05-14 | Dalia Lens | 2012-08-09 11:42 | Story Points |  | 4
B4B-55 | Brand color scheme | To Do |  | 2012-07-21 13:51 | 2012-05-08 | 2012-05-10 | Levente Szabo | 2012-08-09 11:42 | Story Points |  | 4
B4B-49 | Beem Inc. - Company website design | Done | Done | 2012-07-13 17:11 | 2012-05-08 | 2012-05-23 | Levente Szabo | 2012-07-13 17:17 | Attachment |  | mockup.png
B4B-49 | Beem Inc. - Company website design | Done | Done | 2012-07-13 17:11 | 2012-05-08 | 2012-05-23 | Richard Dawkins | 2012-07-11 17:18 | Attachment |  | mockup2.png
B4B-49 | Beem Inc. - Company website design | Done | Done | 2012-07-13 17:11 | 2012-05-08 | 2012-05-23 | Richard Dawkins | 2012-07-12 17:18 | Attachment |  | mockup3.png
B4B-49 | Beem Inc. - Company website design | Done | Done | 2012-07-13 17:11 | 2012-05-08 | 2012-05-23 | Levente Szabo | 2012-07-13 17:18 | labels |  | billable design website
B4B-49 | Beem Inc. - Company website design | Done | Done | 2012-07-13 17:11 | 2012-05-08 | 2012-05-23 | Levente Szabo | 2012-07-13 17:18 | priority | Medium | Highest
B4B-49 | Beem Inc. - Company website design | Done | Done | 2012-07-13 17:11 | 2012-05-08 | 2012-05-23 | Levente Szabo | 2012-07-13 17:18 | status | To Do | In Progress
B4B-49 | Beem Inc. - Company website design | Done | Done | 2012-07-13 17:11 | 2012-05-08 | 2012-05-23 | Levente Szabo | 2012-07-13 17:18 | assignee |  | Dalia Lens
B4B-49 | Beem Inc. - Company website design | Done | Done | 2012-07-13 17:11 | 2012-05-08 | 2012-05-23 | Dalia Lens | 2012-07-13 17:18 | summary | Beem website design | Beem Inc. - Company website design
B4B-49 | Beem Inc. - Company website design | Done | Done | 2012-07-13 17:11 | 2012-05-08 | 2012-05-23 | Robert Mongose | 2012-07-13 17:22 | description |  | Full website design for Beem Inc. based on the attached brief. Timeline is found in the brief, additional visual assets are available at the company.
B4B-49 | Beem Inc. - Company website design | Done | Done | 2012-07-13 17:11 | 2012-05-08 | 2012-05-23 | Levente Szabo | 2012-07-13 17:23 | Attachment |  | Beem website proejct- Design Brief.doc
B4B-49 | Beem Inc. - Company website design | Done | Done | 2012-07-13 17:11 | 2012-05-08 | 2012-05-23 | Owen Klyed | 2012-07-13 17:23 | Attachment | Beem website proejct- Design Brief.doc
B4B-38 | Historical analysis | Done | Done | 2012-05-19 13:44 | 2012-05-22 | 2012-05-30 | Levente Szabo | 2012-05-19 13:47 | priority | Medium | Low
B4B-38 | Historical analysis | Done | Done | 2012-05-19 13:44 | 2012-05-22 | 2012-05-30 | Levente Szabo | 2012-05-19 14:37 | status | To Do | In Progress
B4B-38 | Historical analysis | Done | Done | 2012-05-19 13:44 | 2012-05-22 | 2012-05-30 | Marcus Thiel | 2012-05-22 11:19 | resolution |  | Done
B4B-37 | Online research | Done | Done | 2012-05-19 13:44 | 2012-05-16 | 2012-05-22 | Levente Szabo | 2012-05-19 13:46 | priority | Medium | Low
B4B-37 | Online research | Done | Done | 2012-05-19 13:44 | 2012-05-16 | 2012-05-22 | Casey Ford | 2012-05-19 16:03 | status | To Do | In Progress
B4B-37 | Online research | Done | Done | 2012-05-19 13:44 | 2012-05-16 | 2012-05-22 | Casey Ford | 2012-05-22 14:24 | assignee |  | Owen Klyed
B4B-37 | Online research | Done | Done | 2012-05-19 13:44 | 2012-05-16 | 2012-05-22 | Owen Klyed | 2012-05-22 14:46 | resolution |  | Done
B4B-37 | Online research | Done | Done | 2012-05-19 13:44 | 2012-05-16 | 2012-05-22 | Owen Klyed | 2012-05-22 14:46 | status | In Progress | Done
B4B-37 | Online research | Done | Done | 2012-05-19 13:44 | 2012-05-16 | 2012-05-22 | Owen Klyed | 2012-08-09 11:43 | Story Points |  | 30
B4B-37 | Online research | Done | Done | 2012-05-19 13:44 | 2012-05-16 | 2012-05-22 | Owen Klyed | 2012-08-11 14:56 | labels |  | validation
B4B-36 | Phone interviews | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Levente Szabo | 2012-05-19 13:43 | status | To Do | In Progress
B4B-36 | Phone interviews | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Owen Klyed | 2012-05-19 16:03 | resolution |  | Done
B4B-36 | Phone interviews | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Owen Klyed | 2012-05-19 16:03 | status | In Progress | Done
B4B-36 | Phone interviews | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Owen Klyed | 2012-05-19 16:04 | resolution | Done
B4B-36 | Phone interviews | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Owen Klyed | 2012-05-19 16:03 | status | Done | In Progress
B4B-36 | Phone interviews | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Levente Szabo | 2012-05-19 16:39 | timeestimate |  | 0
B4B-36 | Phone interviews | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Levente Szabo | 2012-05-19 16:39 | timespent |  | 144000
B4B-36 | Phone interviews | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Levente Szabo | 2012-05-19 16:39 | WorklogId | 10403
B4B-36 | Phone interviews | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Levente Szabo | 2012-05-22 11:18 | resolution |  | Done
B4B-36 | Phone interviews | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Levente Szabo | 2012-05-22 11:18 | status | In Progress | Done
B4B-36 | Phone interviews | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Dalia Lens | 2012-05-22 14:20 | summary | Phone intervies | Phone interviews
B4B-36 | Phone interviews | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Levente Szabo | 2012-05-22 14:24 | assignee |  | Owen Klyed
B4B-36 | Phone interviews | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Levente Szabo | 2012-08-09 11:43 | Story Points |  | 40
B4B-36 | Phone interviews | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Levente Szabo | 2012-08-11 14:56 | labels |  | validation
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Owen Klyed | 2012-05-19 13:37 | End Date | 24/May/16 | 27/May/16
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Levente Szabo | 2012-05-19 13:42 | status | To Do | In Progress
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Robert Mongose | 2012-05-19 16:04 | resolution |  | Done
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Robert Mongose | 2012-05-19 16:04 | status | In Progress | Done
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Robert Mongose | 2012-05-19 16:04 | resolution | Done
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Robert Mongose | 2012-05-19 16:04 | status | Done | In Progress
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Robert Mongose | 2012-05-19 16:40 | timeestimate |  | 0
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Robert Mongose | 2012-05-19 16:04 | timespent |  | 600
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Robert Mongose | 2012-05-19 16:04 | WorklogId | 10301
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Owen Klyed | 2012-05-19 16:41 | timespent | 600 | 288000
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Owen Klyed | 2012-05-19 16:41 | WorklogId | 10301
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Dalia Lens | 2012-05-22 10:09 | labels |  | billable
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Owen Klyed | 2012-05-22 10:09 | timespent | 288000 | 576000
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Owen Klyed | 2012-05-22 10:09 | WorklogId | 10400
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Owen Klyed | 2012-05-22 10:14 | timeestimate | 0 | 288000
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Owen Klyed | 2012-05-22 10:09 | timespent | 576000 | 288000
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Owen Klyed | 2012-05-22 10:09 | WorklogId | 10301
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Owen Klyed | 2012-05-22 10:09 | WorklogTimeSpent | 2 weeks
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Dalia Lens | 2012-05-22 10:16 | WorklogId | 10400
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Levente Szabo | 2012-05-22 10:32 | WorklogId | 10400
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Levente Szabo | 2012-05-22 11:18 | resolution |  | Done
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Levente Szabo | 2012-05-22 11:18 | status | In Progress | Done
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Richard Dawkins | 2012-05-22 14:03 | labels | billable
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Levente Szabo | 2012-05-22 14:25 | assignee |  | Owen Klyed
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Levente Szabo | 2012-07-13 16:17 | resolution | Done
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Levente Szabo | 2012-07-13 16:17 | status | Done | In Progress
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Levente Szabo | 2012-07-18 15:51 | resolution |  | Done
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Levente Szabo | 2012-07-18 15:51 | status | In Progress | Done
B4B-35 | In person interviews | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Robert Mongose | 2012-08-09 11:43 | Story Points |  | 40
B4B-34 | Clarify color schemes | In Progress |  | 2012-05-19 11:39 | 2012-05-18 | 2012-05-28 | Levente Szabo | 2012-05-19 11:40 | assignee |  | Dalia Lens
B4B-34 | Clarify color schemes | In Progress |  | 2012-05-19 11:39 | 2012-05-18 | 2012-05-28 | Owen Klyed | 2012-05-19 11:40 | assignee | Dalia Lens | Casey Ford
B4B-34 | Clarify color schemes | In Progress |  | 2012-05-19 11:39 | 2012-05-18 | 2012-05-28 | Levente Szabo | 2012-05-23 13:01 | Story Points |  | 2
B4B-34 | Clarify color schemes | In Progress |  | 2012-05-19 11:39 | 2012-05-18 | 2012-05-28 | Levente Szabo | 2012-07-18 16:50 | resolution |  | Done
B4B-34 | Clarify color schemes | In Progress |  | 2012-05-19 11:39 | 2012-05-18 | 2012-05-28 | Levente Szabo | 2012-07-18 16:50 | status | To Do | Done
B4B-34 | Clarify color schemes | In Progress |  | 2012-05-19 11:39 | 2012-05-18 | 2012-05-28 | Levente Szabo | 2012-07-18 16:50 | status | Done | Done
B4B-34 | Clarify color schemes | In Progress |  | 2012-05-19 11:39 | 2012-05-18 | 2012-05-28 | Casey Ford | 2012-07-18 16:54 | resolution | Done
B4B-34 | Clarify color schemes | In Progress |  | 2012-05-19 11:39 | 2012-05-18 | 2012-05-28 | Casey Ford | 2012-07-18 16:50 | status | Done | In Progress
B4B-33 | Feedback on components | To Do |  | 2012-05-17 15:26 | 2012-05-18 | 2012-05-28 | Owen Klyed | 2012-05-18 12:29 | assignee |  | Dalia Lens
B4B-33 | Feedback on components | To Do |  | 2012-05-17 15:26 | 2012-05-18 | 2012-05-28 | Levente Szabo | 2012-05-23 13:01 | Story Points |  | 2
B4B-32 | Feedback on overall design approach | Done | Done | 2012-05-17 15:25 | 2012-05-18 | 2012-05-28 | Levente Szabo | 2012-05-18 12:29 | assignee |  | Dalia Lens
B4B-32 | Feedback on overall design approach | Done | Done | 2012-05-17 15:25 | 2012-05-18 | 2012-05-28 | Dalia Lens | 2012-05-18 18:17 | assignee | Dalia Lens | Robert Mongose
B4B-32 | Feedback on overall design approach | Done | Done | 2012-05-17 15:25 | 2012-05-18 | 2012-05-28 | Levente Szabo | 2012-05-19 11:56 | assignee | Robert Mongose | Owen Klyed
B4B-32 | Feedback on overall design approach | Done | Done | 2012-05-17 15:25 | 2012-05-18 | 2012-05-28 | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 6
B4B-32 | Feedback on overall design approach | Done | Done | 2012-05-17 15:25 | 2012-05-18 | 2012-05-28 | Owen Klyed | 2012-07-13 16:17 | status | To Do | In Progress
B4B-32 | Feedback on overall design approach | Done | Done | 2012-05-17 15:25 | 2012-05-18 | 2012-05-28 | Levente Szabo | 2012-07-18 15:51 | resolution |  | Done
B4B-32 | Feedback on overall design approach | Done | Done | 2012-05-17 15:25 | 2012-05-18 | 2012-05-28 | Levente Szabo | 2012-07-18 15:51 | status | In Progress | Done
B4B-31 | Collect feedback | To Do |  | 2012-05-17 13:07 | 2012-06-14 | 2012-06-14 | Marcus Thiel | 2012-05-17 13:29 | Sprint |  | Dev sprint 2
B4B-31 | Collect feedback | To Do |  | 2012-05-17 13:07 | 2012-06-14 | 2012-06-14 | Levente Szabo | 2012-05-17 13:29 | Rank |  | Ranked higher
B4B-31 | Collect feedback | To Do |  | 2012-05-17 13:07 | 2012-06-14 | 2012-06-14 | Casey Ford | 2012-05-17 13:29 | Rank |  | Ranked lower
B4B-31 | Collect feedback | To Do |  | 2012-05-17 13:07 | 2012-06-14 | 2012-06-14 | Casey Ford | 2012-05-18 13:43 | priority | Medium | Low
B4B-31 | Collect feedback | To Do |  | 2012-05-17 13:07 | 2012-06-14 | 2012-06-14 | Owen Klyed | 2012-05-23 13:03 | Story Points |  | 8
B4B-31 | Collect feedback | To Do |  | 2012-05-17 13:07 | 2012-06-14 | 2012-06-14 | Levente Szabo | 2012-08-11 14:56 | labels |  | validation
B4B-30 | Set up FB group for beta testers | To Do |  | 2012-05-17 13:06 | 2012-05-29 | 2012-05-29 | Levente Szabo | 2012-05-17 13:29 | Sprint |  | Dev sprint 2
B4B-30 | Set up FB group for beta testers | To Do |  | 2012-05-17 13:06 | 2012-05-29 | 2012-05-29 | Levente Szabo | 2012-05-17 13:29 | Rank |  | Ranked higher
B4B-30 | Set up FB group for beta testers | To Do |  | 2012-05-17 13:06 | 2012-05-29 | 2012-05-29 | Dalia Lens | 2012-05-23 13:02 | Story Points |  | 6
B4B-30 | Set up FB group for beta testers | To Do |  | 2012-05-17 13:06 | 2012-05-29 | 2012-05-29 | Levente Szabo | 2012-07-14 14:19 | labels | CR&mrktg | CRM marketing
B4B-30 | Set up FB group for beta testers | To Do |  | 2012-05-17 13:06 | 2012-05-29 | 2012-05-29 | Levente Szabo | 2012-08-11 14:57 | labels | CRM marketing | CRM marketing validation
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Owen Klyed | 2012-05-17 13:29 | Sprint |  | Dev sprint 2
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-05-17 13:29 | Rank |  | Ranked higher
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 6
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Marcus Thiel | 2012-06-08 11:31 | assignee | Casey Ford | Levente Szabo
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-06-08 11:35 | assignee | Levente Szabo | Casey Ford
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Casey Ford | 2012-06-08 11:41 | assignee | Casey Ford | Levente Szabo
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Casey Ford | 2012-06-08 11:43 | resolution |  | Done
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Casey Ford | 2012-06-08 11:43 | status | To Do | Done
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-06-08 11:45 | status | Done | Done
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-06-08 11:46 | resolution | Done
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-06-08 11:46 | status | Done | In Progress
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-06-08 11:46 | resolution |  | Done
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-06-08 11:46 | status | In Progress | Done
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-07-13 16:17 | resolution | Done
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-07-13 16:17 | status | Done | In Progress
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-07-14 14:19 | labels | CR&mrktg | CRM marketing
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-07-18 15:51 | resolution |  | Done
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Casey Ford | 2012-07-18 15:51 | status | In Progress | Done
B4B-29 | Plan the email campaigns | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-08-11 14:57 | labels | CRM marketing | CRM marketing validation
B4B-28 | Copy for email campaigns | To Do |  | 2012-05-17 13:01 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-05-17 13:02 | Parent |  | B4B-29
B4B-28 | Copy for email campaigns | To Do |  | 2012-05-17 13:01 | 2012-06-13 | 2012-06-20 | Marcus Thiel | 2012-05-17 13:02 | issuetype | Task | Sub-task
B4B-28 | Copy for email campaigns | To Do |  | 2012-05-17 13:01 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-05-18 13:43 | priority | Medium | Low
B4B-28 | Copy for email campaigns | To Do |  | 2012-05-17 13:01 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-05-23 13:03 | Story Points |  | 8
B4B-28 | Copy for email campaigns | To Do |  | 2012-05-17 13:01 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-07-14 14:19 | labels | CR&mrktg | CRM marketing
B4B-27 | Set up Mailchimp | In Progress |  | 2012-05-17 12:58 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-05-17 13:29 | Rank |  | Ranked lower
B4B-27 | Set up Mailchimp | In Progress |  | 2012-05-17 12:58 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-05-17 13:29 | Sprint |  | Dev sprint 2
B4B-27 | Set up Mailchimp | In Progress |  | 2012-05-17 12:58 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-05-17 13:29 | Rank |  | Ranked higher
B4B-27 | Set up Mailchimp | In Progress |  | 2012-05-17 12:58 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-05-17 13:29 | Rank |  | Ranked lower
B4B-27 | Set up Mailchimp | In Progress |  | 2012-05-17 12:58 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-05-18 13:42 | priority | Medium | Low
B4B-27 | Set up Mailchimp | In Progress |  | 2012-05-17 12:58 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-05-23 13:03 | Story Points |  | 8
B4B-27 | Set up Mailchimp | In Progress |  | 2012-05-17 12:58 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-07-13 16:17 | status | To Do | In Progress
B4B-27 | Set up Mailchimp | In Progress |  | 2012-05-17 12:58 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-07-14 14:19 | labels | CR&mrktg | CRM marketing
B4B-27 | Set up Mailchimp | In Progress |  | 2012-05-17 12:58 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-08-09 11:29 | timeestimate |  | 0
B4B-27 | Set up Mailchimp | In Progress |  | 2012-05-17 12:58 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-08-09 11:29 | timespent |  | 18000
B4B-27 | Set up Mailchimp | In Progress |  | 2012-05-17 12:58 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-08-09 11:29 | WorklogId | 20500
B4B-27 | Set up Mailchimp | In Progress |  | 2012-05-17 12:58 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-08-09 11:29 | summary | Set up Maichimp | Set up Mailchimp
B4B-26 | Set up Hootsuite account | To Do |  | 2012-05-17 12:57 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-05-17 13:29 | Sprint |  | Dev sprint 2
B4B-26 | Set up Hootsuite account | To Do |  | 2012-05-17 12:57 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-05-23 13:01 | Story Points |  | 2
B4B-26 | Set up Hootsuite account | To Do |  | 2012-05-17 12:57 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-07-14 14:19 | labels | CR&mrktg | CRM marketing
B4B-25 | "React" feature | To Do |  | 2012-05-17 12:55 | 2012-06-09 | 2012-06-13 | Levente Szabo | 2012-05-18 15:14 | summary | Create the "React" feature | "React" feature
B4B-25 | "React" feature | To Do |  | 2012-05-17 12:55 | 2012-06-09 | 2012-06-13 | Levente Szabo | 2012-05-18 16:25 | timeestimate |  | 0
B4B-25 | "React" feature | To Do |  | 2012-05-17 12:55 | 2012-06-09 | 2012-06-13 | Owen Klyed | 2012-05-18 16:25 | timespent |  | 115200
B4B-25 | "React" feature | To Do |  | 2012-05-17 12:55 | 2012-06-09 | 2012-06-13 | Owen Klyed | 2012-05-18 16:25 | WorklogId | 10202
B4B-25 | "React" feature | To Do |  | 2012-05-17 12:55 | 2012-06-09 | 2012-06-13 | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 6
B4B-25 | "React" feature | To Do |  | 2012-05-17 12:55 | 2012-06-09 | 2012-06-13 | Levente Szabo | 2012-06-08 16:53 | assignee | Robert Mongose
B4B-25 | "React" feature | To Do |  | 2012-05-17 12:55 | 2012-06-09 | 2012-06-13 | Levente Szabo | 2012-06-08 17:15 | timeoriginalestimate |  | 0
B4B-25 | "React" feature | To Do |  | 2012-05-17 12:55 | 2012-06-09 | 2012-06-13 | Owen Klyed | 2012-06-08 17:15 | assignee |  | Dalia Lens
B4B-25 | "React" feature | To Do |  | 2012-05-17 12:55 | 2012-06-09 | 2012-06-13 | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
B4B-24 | Video feed | Done | Done | 2012-05-17 12:54 | 2012-06-06 | 2012-06-09 | Levente Szabo | 2012-05-18 15:14 | summary | Implement video feed | Video feed
B4B-24 | Video feed | Done | Done | 2012-05-17 12:54 | 2012-06-06 | 2012-06-09 | Levente Szabo | 2012-05-18 16:31 | timeestimate |  | 0
B4B-24 | Video feed | Done | Done | 2012-05-17 12:54 | 2012-06-06 | 2012-06-09 | Levente Szabo | 2012-05-18 16:31 | timespent |  | 86400
B4B-24 | Video feed | Done | Done | 2012-05-17 12:54 | 2012-06-06 | 2012-06-09 | Levente Szabo | 2012-05-18 16:31 | WorklogId | 10203
B4B-24 | Video feed | Done | Done | 2012-05-17 12:54 | 2012-06-06 | 2012-06-09 | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 6
B4B-24 | Video feed | Done | Done | 2012-05-17 12:54 | 2012-06-06 | 2012-06-09 | Levente Szabo | 2012-06-08 16:53 | assignee | Robert Mongose
B4B-24 | Video feed | Done | Done | 2012-05-17 12:54 | 2012-06-06 | 2012-06-09 | Levente Szabo | 2012-06-08 17:15 | timeoriginalestimate |  | 0
B4B-24 | Video feed | Done | Done | 2012-05-17 12:54 | 2012-06-06 | 2012-06-09 | Owen Klyed | 2012-06-08 17:15 | assignee |  | Dalia Lens
B4B-24 | Video feed | Done | Done | 2012-05-17 12:54 | 2012-06-06 | 2012-06-09 | Levente Szabo | 2012-07-13 16:17 | status | To Do | In Progress
B4B-24 | Video feed | Done | Done | 2012-05-17 12:54 | 2012-06-06 | 2012-06-09 | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
B4B-24 | Video feed | Done | Done | 2012-05-17 12:54 | 2012-06-06 | 2012-06-09 | Levente Szabo | 2012-07-18 15:51 | resolution |  | Done
B4B-24 | Video feed | Done | Done | 2012-05-17 12:54 | 2012-06-06 | 2012-06-09 | Owen Klyed | 2012-07-18 15:51 | status | In Progress | Done
B4B-23 | Video sharing feature | To Do |  | 2012-05-17 12:53 | 2012-06-02 | 2012-06-06 | Levente Szabo | 2012-05-18 13:49 | priority | Medium | Low
B4B-23 | Video sharing feature | To Do |  | 2012-05-17 12:53 | 2012-06-02 | 2012-06-06 | Levente Szabo | 2012-05-18 14:56 | summary | Implement video sharing feature | New Feature - Implement video sharing feature
B4B-23 | Video sharing feature | To Do |  | 2012-05-17 12:53 | 2012-06-02 | 2012-06-06 | Levente Szabo | 2012-05-18 14:59 | summary | New Feature - Implement video sharing feature | "New Feature" - Implement video sharing feature
B4B-23 | Video sharing feature | To Do |  | 2012-05-17 12:53 | 2012-06-02 | 2012-06-06 | Levente Szabo | 2012-05-18 15:03 | summary | "New Feature" - Implement video sharing feature | Implement video sharing feature
B4B-23 | Video sharing feature | To Do |  | 2012-05-17 12:53 | 2012-06-02 | 2012-06-06 | Levente Szabo | 2012-05-18 15:09 | summary | Implement video sharing feature | Video sharing feature
B4B-23 | Video sharing feature | To Do |  | 2012-05-17 12:53 | 2012-06-02 | 2012-06-06 | Levente Szabo | 2012-05-23 13:03 | Story Points |  | 8
B4B-23 | Video sharing feature | To Do |  | 2012-05-17 12:53 | 2012-06-02 | 2012-06-06 | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-18 15:13 | summary | Implement video recording feature | Video recording feature
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-18 16:31 | timeestimate |  | 0
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Owen Klyed | 2012-05-18 16:31 | timespent |  | 115200
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Owen Klyed | 2012-05-18 16:31 | WorklogId | 10204
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-19 12:38 | Attachment |  | Components.docx
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-19 12:43 | description | Create and test the video recording feature. (The main feature!!) | The video recording feature is the core feature of the MVP so we need to ensure that we deliver this in great quality and on time. {code:java} public int getFpsRate() { return stream.fpsRate; } {code}
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-19 12:45 | summary | Video recording feature | Video recording feature xxx
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-19 12:51 | description | The video recording feature is the core feature of the MVP so we need to ensure that we deliver this in great quality and on time. {code:java} public int getFpsRate() { return stream.fpsRate; } {code} | The video recording feature is the core feature of the MVP so we need to ensure that we deliver this in great quality and on time! Guys, for starters, make sure that when you call the FpsRate getter the stream isn't null, the feature will only work this way! If you have any questions pls turn immediately to me or [~robert], he is an expert on this. {code:java} public int getFpsRate() { return stream.fpsRate; } {code}
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-19 12:53 | Attachment | Components.docx
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-19 12:54 | Attachment |  | Video Streaming Architecture.docx
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-19 12:54 | summary | Video recording feature xxx | Video recording feature
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-19 12:56 | Attachment |  | Video streaming.jpg
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-19 12:56 | Attachment | Video streaming.jpg
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-19 12:56 | Attachment |  | Video streaming.psd.jpg
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-19 12:56 | Attachment | Video streaming.psd.jpg
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-19 12:58 | Attachment |  | Graphical requirements.docx
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-19 13:04 | Attachment |  | Stream screen design.psd
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 4
B4B-22 | Video recording feature | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-17 12:42 | Start Date | 28/Jun/16 | 11/May/16
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-17 12:42 | End Date | 12/Jul/16 | 27/Jul/16
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-17 12:42 | End Date | 27/Jul/16 | 27/May/16
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-17 13:28 | Sprint |  | Dev sprint
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-17 13:28 | Rank |  | Ranked higher
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-22 10:17 | labels | IT&Dev | IT&Dev billable
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-22 10:19 | timeestimate |  | 0
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Dalia Lens | 2012-05-22 10:19 | timespent |  | 432000
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Dalia Lens | 2012-05-22 10:19 | WorklogId | 10401
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-22 12:38 | issuetype | Task | Epic
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-22 14:08 | timespent | 432000 | 506040
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Dalia Lens | 2012-05-22 10:19 | WorklogId | 10401
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-22 10:19 | timeestimate | 0 | 144000
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Dalia Lens | 2012-05-22 10:19 | timespent | 506040 | 362040
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Dalia Lens | 2012-05-22 10:19 | WorklogId | 10401
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-22 10:19 | timeestimate | 144000 | 0
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Dalia Lens | 2012-05-22 10:19 | timespent | 362040 | 506040
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Dalia Lens | 2012-05-22 10:19 | WorklogId | 10403
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Dalia Lens | 2012-05-22 14:10 | WorklogId | 10403
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-22 14:12 | timespent | 506040 | 524040
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Dalia Lens | 2012-05-22 10:19 | WorklogId | 10403
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-22 16:21 | WorklogId | 10403
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-22 16:21 | WorklogId | 10401
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 4
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-06-08 16:54 | assignee |  | Levente Szabo
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-06-09 10:09 | resolution |  | Done
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Dalia Lens | 2012-06-09 10:09 | status | To Do | Done
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev billable | DEV IT
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-08-11 14:57 | labels | DEV IT | DEV IT validation
B4B-21 | Implement MVP functions | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-08-11 15:02 | labels | DEV IT validation | DEV IT
B4B-20 | Log-in form | To Do |  | 2012-05-16 11:04 | 2012-05-24 | 2012-05-26 | Levente Szabo | 2012-05-16 11:04 | Start Date | 23/May/16 | 25/May/16
B4B-20 | Log-in form | To Do |  | 2012-05-16 11:04 | 2012-05-24 | 2012-05-26 | Levente Szabo | 2012-05-16 11:04 | End Date | 25/May/16 | 27/May/16
B4B-20 | Log-in form | To Do |  | 2012-05-16 11:04 | 2012-05-24 | 2012-05-26 | Levente Szabo | 2012-05-17 12:47 | Parent |  | B4B-21
B4B-20 | Log-in form | To Do |  | 2012-05-16 11:04 | 2012-05-24 | 2012-05-26 | Dalia Lens | 2012-05-17 12:47 | issuetype | Task | Sub-task
B4B-20 | Log-in form | To Do |  | 2012-05-16 11:04 | 2012-05-24 | 2012-05-26 | Levente Szabo | 2012-05-18 15:08 | summary | Create log-in form | Log-in form
B4B-20 | Log-in form | To Do |  | 2012-05-16 11:04 | 2012-05-24 | 2012-05-26 | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 4
B4B-20 | Log-in form | To Do |  | 2012-05-16 11:04 | 2012-05-24 | 2012-05-26 | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
B4B-19 | Sign-up form | In Progress |  | 2012-05-16 11:03 | 2012-05-22 | 2012-05-24 | Levente Szabo | 2012-05-16 11:03 | Link |  | This issue is blocked by B4B-9
B4B-19 | Sign-up form | In Progress |  | 2012-05-16 11:03 | 2012-05-22 | 2012-05-24 | Levente Szabo | 2012-05-17 12:49 | Parent |  | B4B-21
B4B-19 | Sign-up form | In Progress |  | 2012-05-16 11:03 | 2012-05-22 | 2012-05-24 | Owen Klyed | 2012-05-17 12:49 | issuetype | Task | Sub-task
B4B-19 | Sign-up form | In Progress |  | 2012-05-16 11:03 | 2012-05-22 | 2012-05-24 | Levente Szabo | 2012-05-18 15:11 | summary | Create reg form | Registration form
B4B-19 | Sign-up form | In Progress |  | 2012-05-16 11:03 | 2012-05-22 | 2012-05-24 | Levente Szabo | 2012-05-18 16:31 | timeestimate |  | 0
B4B-19 | Sign-up form | In Progress |  | 2012-05-16 11:03 | 2012-05-22 | 2012-05-24 | Owen Klyed | 2012-05-18 16:31 | timespent |  | 57600
B4B-19 | Sign-up form | In Progress |  | 2012-05-16 11:03 | 2012-05-22 | 2012-05-24 | Owen Klyed | 2012-05-18 16:31 | WorklogId | 10205
B4B-19 | Sign-up form | In Progress |  | 2012-05-16 11:03 | 2012-05-22 | 2012-05-24 | Levente Szabo | 2012-05-22 16:49 | assignee | Robert Mongose | Levente Szabo
B4B-19 | Sign-up form | In Progress |  | 2012-05-16 11:03 | 2012-05-22 | 2012-05-24 | Levente Szabo | 2012-05-22 16:49 | summary | Registration form | Sign-up form
B4B-19 | Sign-up form | In Progress |  | 2012-05-16 11:03 | 2012-05-22 | 2012-05-24 | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 4
B4B-19 | Sign-up form | In Progress |  | 2012-05-16 11:03 | 2012-05-22 | 2012-05-24 | Levente Szabo | 2012-07-13 16:17 | status | To Do | In Progress
B4B-19 | Sign-up form | In Progress |  | 2012-05-16 11:03 | 2012-05-22 | 2012-05-24 | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
B4B-18 | Tutorial section | Done | Done | 2012-05-16 10:59 | 2012-05-16 | 2012-05-22 | Levente Szabo | 2012-05-17 12:50 | Parent |  | B4B-21
B4B-18 | Tutorial section | Done | Done | 2012-05-16 10:59 | 2012-05-16 | 2012-05-22 | Owen Klyed | 2012-05-17 12:50 | issuetype | Task | Sub-task
B4B-18 | Tutorial section | Done | Done | 2012-05-16 10:59 | 2012-05-16 | 2012-05-22 | Levente Szabo | 2012-05-18 15:09 | assignee | Robert Mongose | Levente Szabo
B4B-18 | Tutorial section | Done | Done | 2012-05-16 10:59 | 2012-05-16 | 2012-05-22 | Levente Szabo | 2012-05-18 15:09 | summary | Implement and test "Intro section" | Tutorial section
B4B-18 | Tutorial section | Done | Done | 2012-05-16 10:59 | 2012-05-16 | 2012-05-22 | Levente Szabo | 2012-05-18 15:09 | assignee | Levente Szabo | Dalia Lens
B4B-18 | Tutorial section | Done | Done | 2012-05-16 10:59 | 2012-05-16 | 2012-05-22 | Levente Szabo | 2012-05-18 16:59 | timeestimate |  | 0
B4B-18 | Tutorial section | Done | Done | 2012-05-16 10:59 | 2012-05-16 | 2012-05-22 | Owen Klyed | 2012-05-18 16:59 | timespent |  | 144000
B4B-18 | Tutorial section | Done | Done | 2012-05-16 10:59 | 2012-05-16 | 2012-05-22 | Owen Klyed | 2012-05-18 16:59 | WorklogId | 10206
B4B-18 | Tutorial section | Done | Done | 2012-05-16 10:59 | 2012-05-16 | 2012-05-22 | Levente Szabo | 2012-05-22 14:46 | resolution |  | Done
B4B-18 | Tutorial section | Done | Done | 2012-05-16 10:59 | 2012-05-16 | 2012-05-22 | Owen Klyed | 2012-05-22 14:46 | status | To Do | Done
B4B-18 | Tutorial section | Done | Done | 2012-05-16 10:59 | 2012-05-16 | 2012-05-22 | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
B4B-18 | Tutorial section | Done | Done | 2012-05-16 10:59 | 2012-05-16 | 2012-05-22 | Levente Szabo | 2012-08-09 11:38 | Story Points |  | 14
B4B-17 | Set up cloud hosting | Done | Done | 2012-05-16 10:54 | 2012-05-15 | 2012-05-15 | Levente Szabo | 2012-05-16 11:01 | Start Date | 6/Jun/16 | 16/May/16
B4B-17 | Set up cloud hosting | Done | Done | 2012-05-16 10:54 | 2012-05-15 | 2012-05-15 | Levente Szabo | 2012-05-16 11:01 | End Date | 6/Jun/16 | 16/May/16
B4B-17 | Set up cloud hosting | Done | Done | 2012-05-16 10:54 | 2012-05-15 | 2012-05-15 | Levente Szabo | 2012-05-17 13:28 | Sprint |  | Dev sprint
B4B-17 | Set up cloud hosting | Done | Done | 2012-05-16 10:54 | 2012-05-15 | 2012-05-15 | Levente Szabo | 2012-05-18 13:48 | priority | Medium | Low
B4B-17 | Set up cloud hosting | Done | Done | 2012-05-16 10:54 | 2012-05-15 | 2012-05-15 | Levente Szabo | 2012-05-22 14:45 | resolution |  | Done
B4B-17 | Set up cloud hosting | Done | Done | 2012-05-16 10:54 | 2012-05-15 | 2012-05-15 | Owen Klyed | 2012-05-22 14:45 | status | To Do | Done
B4B-17 | Set up cloud hosting | Done | Done | 2012-05-16 10:54 | 2012-05-15 | 2012-05-15 | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
B4B-17 | Set up cloud hosting | Done | Done | 2012-05-16 10:54 | 2012-05-15 | 2012-05-15 | Levente Szabo | 2012-08-09 11:39 | Story Points |  | 18
B4B-16 | Set up Dev Environment | Done | Done | 2012-05-16 10:52 | 2012-05-11 | 2012-05-15 | Levente Szabo | 2012-05-16 11:01 | Start Date | 2/Jun/16 | 12/May/16
B4B-16 | Set up Dev Environment | Done | Done | 2012-05-16 10:52 | 2012-05-11 | 2012-05-15 | Levente Szabo | 2012-05-16 11:01 | End Date | 6/Jun/16 | 16/May/16
B4B-16 | Set up Dev Environment | Done | Done | 2012-05-16 10:52 | 2012-05-11 | 2012-05-15 | Levente Szabo | 2012-05-17 13:28 | Sprint |  | Dev sprint
B4B-16 | Set up Dev Environment | Done | Done | 2012-05-16 10:52 | 2012-05-11 | 2012-05-15 | Levente Szabo | 2012-05-22 14:44 | resolution |  | Done
B4B-16 | Set up Dev Environment | Done | Done | 2012-05-16 10:52 | 2012-05-11 | 2012-05-15 | Levente Szabo | 2012-05-22 14:44 | status | To Do | Done
B4B-16 | Set up Dev Environment | Done | Done | 2012-05-16 10:52 | 2012-05-11 | 2012-05-15 | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
B4B-16 | Set up Dev Environment | Done | Done | 2012-05-16 10:52 | 2012-05-11 | 2012-05-15 | Levente Szabo | 2012-08-09 11:39 | Story Points |  | 8
B4B-15 | Set up DB | Done | Done | 2012-05-16 10:51 | 2012-05-10 | 2012-05-10 | Levente Szabo | 2012-05-16 11:00 | Start Date | 1/Jun/16 | 11/May/16
B4B-15 | Set up DB | Done | Done | 2012-05-16 10:51 | 2012-05-10 | 2012-05-10 | Levente Szabo | 2012-05-16 11:00 | End Date | 1/Jun/16 | 11/May/16
B4B-15 | Set up DB | Done | Done | 2012-05-16 10:51 | 2012-05-10 | 2012-05-10 | Levente Szabo | 2012-05-17 13:28 | Sprint |  | Dev sprint
B4B-15 | Set up DB | Done | Done | 2012-05-16 10:51 | 2012-05-10 | 2012-05-10 | Levente Szabo | 2012-05-22 14:44 | resolution |  | Done
B4B-15 | Set up DB | Done | Done | 2012-05-16 10:51 | 2012-05-10 | 2012-05-10 | Owen Klyed | 2012-05-22 14:44 | status | To Do | Done
B4B-15 | Set up DB | Done | Done | 2012-05-16 10:51 | 2012-05-10 | 2012-05-10 | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
B4B-15 | Set up DB | Done | Done | 2012-05-16 10:51 | 2012-05-10 | 2012-05-10 | Levente Szabo | 2012-08-09 11:40 | Story Points |  | 4
B4B-14 | Create landing page | To Do |  | 2012-05-14 21:41 | 2012-06-20 | 2012-06-22 | Levente Szabo | 2012-05-14 21:41 | Link |  | This issue is blocked by B4B-13
B4B-14 | Create landing page | To Do |  | 2012-05-14 21:41 | 2012-06-20 | 2012-06-22 | Levente Szabo | 2012-05-14 22:00 | description | Based on design and copy version testing create final landing page for the service. | Based on design and copy version testing create final landing page for the service, optimized for conversion and social sharing.
B4B-14 | Create landing page | To Do |  | 2012-05-14 21:41 | 2012-06-20 | 2012-06-22 | Levente Szabo | 2012-05-17 13:04 | summary | Create landing apge | Create landing page
B4B-14 | Create landing page | To Do |  | 2012-05-14 21:41 | 2012-06-20 | 2012-06-22 | Levente Szabo | 2012-05-17 13:27 | Sprint |  | UX&UI sprint 2
B4B-14 | Create landing page | To Do |  | 2012-05-14 21:41 | 2012-06-20 | 2012-06-22 | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 6
B4B-14 | Create landing page | To Do |  | 2012-05-14 21:41 | 2012-06-20 | 2012-06-22 | Levente Szabo | 2012-08-11 14:58 | labels | web | validation web
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-05-14 21:36 | Link |  | This issue is blocked by B4B-12
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-05-14 21:41 | Link |  | This issue blocks B4B-14
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-05-14 21:42 | labels |  | web
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-05-17 13:27 | Sprint |  | UX&UI sprint 2
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 6
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-06-05 09:53 | summary | Decide on Landing page | Decision on Landing page
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-06-05 09:53 | summary | Decision on Landing page | Decision on Landing page design
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-06-05 09:53 | summary | Decision on Landing page design | Decision on landing page design
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-06-05 10:03 | description | Based on Unbounce testing make decision on landing page design. | This is an All-Hands decision so all team members are welcome to weigh in with their opinion in the comment section. Please share your view in the comments so we can have everyone's opinion in one place. By the decision time we will have had many debates, A/B tests and some UX tests run so we should have enough data to work with.
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-06-05 10:03 | status | To Do | In Progress
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-06-05 10:03 | Component |  | Landing Page
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-06-05 10:05 | description | This is an All-Hands decision so all team members are welcome to weigh in with their opinion in the comment section. Please share your view in the comments so we can have everyone's opinion in one place. By the decision time we will have had many debates, A/B tests and some UX tests run so we should have enough data to work with. | This is an All-Hands decision so all team members are welcome to weigh in with their opinion in the comment section. Please share your view in the comments on all components, namely the copy, the design, the timing, the highlighted features, so we can have everyone's opinion in one place. By the decision time we will have had many debates, A/B tests and some UX tests run so we should have enough data to work with.
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-06-05 10:09 | Attachment |  | Graphical requirements.docx
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-06-05 10:10 | Attachment |  | landingpage1.png
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-06-05 10:11 | description | This is an All-Hands decision so all team members are welcome to weigh in with their opinion in the comment section. Please share your view in the comments on all components, namely the copy, the design, the timing, the highlighted features, so we can have everyone's opinion in one place. By the decision time we will have had many debates, A/B tests and some UX tests run so we should have enough data to work with. | This is an *All-Hands decision* so all team members are welcome to weigh in with their opinion in the comment section. Please share your view in the comments on all components, namely the copy, the design, the timing, the highlighted features, so we can have everyone's opinion in one place. By the decision time we will have had many debates, A/B tests and some UX tests run so we should have enough data to work with.
B4B-13 | Decision on landing page design | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-06-05 10:35 | description | This is an *All-Hands decision* so all team members are welcome to weigh in with their opinion in the comment section. Please share your view in the comments on all components, namely the copy, the design, the timing, the highlighted features, so we can have everyone's opinion in one place. By the decision time we will have had many debates, A/B tests and some UX tests run so we should have enough data to work with. | This is an *All-Hands decision* so all team members are welcome to weigh in with their opinion in the comment section. Please share your view in the comments {color:red}on all components{color}, namely the copy, the design, the timing, the highlighted features, so we can have everyone's opinion in one place. By the decision time we will have had many debates, A/B tests and some UX tests run so we should have enough data to work with.
B4B-12 | A/B test landing page | In Progress |  | 2012-05-14 19:50 | 2012-06-05 | 2012-06-19 | Levente Szabo | 2012-05-14 19:50 | Link |  | This issue is blocked by B4B-11
B4B-12 | A/B test landing page | In Progress |  | 2012-05-14 19:50 | 2012-06-05 | 2012-06-19 | Levente Szabo | 2012-05-14 19:50 | labels |  | web
B4B-12 | A/B test landing page | In Progress |  | 2012-05-14 19:50 | 2012-06-05 | 2012-06-19 | Levente Szabo | 2012-05-14 21:36 | Link |  | This issue blocks B4B-13
B4B-12 | A/B test landing page | In Progress |  | 2012-05-14 19:50 | 2012-06-05 | 2012-06-19 | Levente Szabo | 2012-05-17 13:27 | Sprint |  | UX&UI sprint 2
B4B-12 | A/B test landing page | In Progress |  | 2012-05-14 19:50 | 2012-06-05 | 2012-06-19 | Levente Szabo | 2012-05-18 13:43 | priority | Medium | Low
B4B-12 | A/B test landing page | In Progress |  | 2012-05-14 19:50 | 2012-06-05 | 2012-06-19 | Levente Szabo | 2012-05-23 13:03 | Story Points |  | 8
B4B-12 | A/B test landing page | In Progress |  | 2012-05-14 19:50 | 2012-06-05 | 2012-06-19 | Levente Szabo | 2012-07-13 16:17 | status | To Do | In Progress
B4B-11 | Landing page copy | In Progress |  | 2012-05-14 19:47 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-14 19:48 | assignee |  | Dalia Lens
B4B-11 | Landing page copy | In Progress |  | 2012-05-14 19:47 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-14 19:48 | labels |  | web
B4B-11 | Landing page copy | In Progress |  | 2012-05-14 19:47 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-14 19:50 | Link |  | This issue blocks B4B-12
B4B-11 | Landing page copy | In Progress |  | 2012-05-14 19:47 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-17 13:27 | Sprint |  | UX&UI sprint 2
B4B-11 | Landing page copy | In Progress |  | 2012-05-14 19:47 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-22 10:20 | timeestimate |  | 0
B4B-11 | Landing page copy | In Progress |  | 2012-05-14 19:47 | 2012-05-31 | 2012-06-02 | Owen Klyed | 2012-05-22 10:20 | timespent |  | 57600
B4B-11 | Landing page copy | In Progress |  | 2012-05-14 19:47 | 2012-05-31 | 2012-06-02 | Owen Klyed | 2012-05-22 10:20 | WorklogId | 10402
B4B-11 | Landing page copy | In Progress |  | 2012-05-14 19:47 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-22 10:21 | labels | web | billable web
B4B-11 | Landing page copy | In Progress |  | 2012-05-14 19:47 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 6
B4B-11 | Landing page copy | In Progress |  | 2012-05-14 19:47 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-07-13 16:17 | status | To Do | In Progress
B4B-11 | Landing page copy | In Progress |  | 2012-05-14 19:47 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-08-11 14:58 | labels | billable web | billable validation web
B4B-10 | Design Feedback (3.) | To Do |  | 2012-05-14 19:42 | 2012-05-23 | 2012-05-23 | Levente Szabo | 2012-05-14 19:42 | Link |  | This issue blocks B4B-9
B4B-10 | Design Feedback (3.) | To Do |  | 2012-05-14 19:42 | 2012-05-23 | 2012-05-23 | Levente Szabo | 2012-05-17 13:26 | Sprint |  | UX&UI sprint
B4B-10 | Design Feedback (3.) | To Do |  | 2012-05-14 19:42 | 2012-05-23 | 2012-05-23 | Levente Szabo | 2012-05-23 13:01 | Story Points |  | 2
B4B-10 | Design Feedback (3.) | To Do |  | 2012-05-14 19:42 | 2012-05-23 | 2012-05-23 | Levente Szabo | 2012-07-14 14:21 | labels | UI&UX | user-experience user-interface
B4B-9 | Design Feedback (2.) | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-14 19:37 | labels |  | UI&UX
B4B-9 | Design Feedback (2.) | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-14 19:42 | Link |  | This issue is blocked by B4B-10
B4B-9 | Design Feedback (2.) | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-16 11:03 | Link |  | This issue blocks B4B-19
B4B-9 | Design Feedback (2.) | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-17 13:26 | Sprint |  | UX&UI sprint
B4B-9 | Design Feedback (2.) | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-17 13:26 | Rank |  | Ranked higher
B4B-9 | Design Feedback (2.) | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-17 13:26 | Rank |  | Ranked lower
B4B-9 | Design Feedback (2.) | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-22 14:45 | resolution |  | Done
B4B-9 | Design Feedback (2.) | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-22 14:45 | status | To Do | Done
B4B-9 | Design Feedback (2.) | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-22 14:59 | resolution | Done
B4B-9 | Design Feedback (2.) | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-22 14:45 | status | Done | To Do
B4B-9 | Design Feedback (2.) | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 4
B4B-9 | Design Feedback (2.) | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-07-13 18:02 | resolution |  | Done
B4B-9 | Design Feedback (2.) | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-07-13 18:02 | status | To Do | Done
B4B-9 | Design Feedback (2.) | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-07-14 14:21 | labels | UI&UX | user-experience user-interface
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-14 19:29 | Link |  | This issue relates to B4B-7
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-14 19:37 | labels |  | UI&UX
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 13:26 | Sprint |  | UX&UI sprint
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 13:33 | Attachment |  | landingpage1.png
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 13:33 | Attachment |  | landingpage2.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 13:34 | Component |  | Landing Page
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 13:36 | Attachment | landingpage2.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 13:36 | Attachment | landingpage1.png
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 13:37 | Attachment |  | landingpage1.png
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 13:33 | Attachment |  | landingpage2.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 13:37 | Attachment | landingpage1.png
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 14:16 | Attachment |  | landingpage1.png
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 14:17 | Attachment | landingpage1.png
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 15:30 | Attachment |  | Components.txt
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 13:33 | Attachment |  | Meeting minutes - Graphic design feedback(1).docx
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 16:02 | description | Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed) | _To be present: UI project team lead, product manager, designers_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed)
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 16:03 | description | _To be present: UI project team lead, product manager, designers_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed) | __To be present: UI project team lead, product manager, designers. Please come prepared!_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed)
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 16:03 | description | __To be present: UI project team lead, product manager, designers. Please come prepared!_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed) | To be present: UI project team lead, product manager, designers. Please come prepared!_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed)
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 16:03 | description | To be present: UI project team lead, product manager, designers. Please come prepared!_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed) | _To be present: UI project team lead, product manager, designers. Please come prepared!_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed)
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 16:06 | description | _To be present: UI project team lead, product manager, designers. Please come prepared!_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed) | _To be present: UI project team lead, product manager, designers. Please come prepared!_ *First design feedback meeting* During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. Give follow-up briefing if needed (most probably needed) * Request corrective actions and/or clear out all remaining concerns
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 16:06 | description | _To be present: UI project team lead, product manager, designers. Please come prepared!_ *First design feedback meeting* During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. Give follow-up briefing if needed (most probably needed) * Request corrective actions and/or clear out all remaining concerns | _To be present: UI project team lead, product manager, designers. Please come prepared!_ *First design feedback meeting* During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed) * Request corrective actions and/or clear out all remaining concerns
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 16:07 | description | _To be present: UI project team lead, product manager, designers. Please come prepared!_ *First design feedback meeting* During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed) * Request corrective actions and/or clear out all remaining concerns | _To be present: UI project team lead, product manager, designers. Please come prepared!_(i) *First design feedback meeting* During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed:)) * Request corrective actions and/or clear out all remaining concerns
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 16:08 | description | _To be present: UI project team lead, product manager, designers. Please come prepared!_(i) *First design feedback meeting* During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed:)) * Request corrective actions and/or clear out all remaining concerns | _To be present: UI project team lead, product manager, designers. Please come prepared!_(i) +*First design feedback meeting*+ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed:)) * Request corrective actions and/or clear out all remaining concerns
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 16:26 | Attachment | Meeting minutes - Graphic design feedback(1).docx
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 16:26 | Attachment |  | Meeting minutes.docx
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 17:37 | labels | UI&UX | UI UX
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-17 17:37 | Component |  | Grid
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-18 12:20 | Link |  | This issue relates to B4B-6
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-18 17:55 | Component |  | Android App
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens |  | Component |  | iOS App
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens |  | Component | Grid
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-18 17:56 | labels | UI UX | UI UX interactions
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-18 17:57 | labels | UI UX interactions | UI UX interactions user-experience user-inteface
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-18 17:58 | labels | UI UX interactions user-experience user-inteface | interactions user-experience user-inteface
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-18 17:58 | labels | interactions user-experience user-inteface | interactions user-experience user-interface
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-18 17:59 | Link |  | This issue is blocked by B4B-7
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-18 17:59 | Link | This issue relates to B4B-7
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-18 17:59 | Link |  | This issue relates to B4B-4
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-18 18:02 | description | _To be present: UI project team lead, product manager, designers. Please come prepared!_(i) +*First design feedback meeting*+ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed:)) * Request corrective actions and/or clear out all remaining concerns | _To be present: UI project team lead, product manager, designers. Please come prepared!_ (on) +*First design feedback meeting*+ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed:)) * Request corrective actions and/or clear out all remaining concerns
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-18 18:02 | description | _To be present: UI project team lead, product manager, designers. Please come prepared!_ (on) +*First design feedback meeting*+ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed:)) * Request corrective actions and/or clear out all remaining concerns | _To be present: UI project team lead, product manager, designers. Please come prepared!_ (on) +*First design feedback meeting*+ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed :)) * Request corrective actions and/or clear out all remaining concerns
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:29 | Attachment | Components.txt
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:29 | Attachment |  | Screen mockups.psd
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:32 | Attachment | landingpage2.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:32 | Attachment |  | mockups-login.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:33 | Attachment | mockups-login.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:33 | Attachment |  | mockups-login.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:42 | timeestimate |  | 0
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:42 | timespent |  | 5400
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:42 | WorklogId | 10207
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:44 | timespent | 5400 | 7200
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:42 | WorklogId | 10208
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:51 | Attachment |  | landingpage2.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:52 | Attachment | landingpage2.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:53 | Attachment | mockups-login.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:53 | Attachment |  | mockups-login.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:59 | Attachment | mockups-login.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 11:59 | Attachment |  | mockups-login.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 17:31 | Attachment | mockups-login.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 17:32 | Attachment |  | mockups-login2.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 22:30 | Attachment | mockups-login2.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-19 22:31 | Attachment |  | mockups-login.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-22 09:53 | Attachment | mockups-login.jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-22 09:53 | Attachment |  | login (1).jpg
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-22 14:35 | resolution |  | Done
B4B-8 | Design Feedback (1.) | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-22 14:35 | status | To Do | Done
B4B-7 | Graphic designer briefing (1.) | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Levente Szabo | 2012-05-14 19:18 | Link |  | This issue is blocked by B4B-6
B4B-7 | Graphic designer briefing (1.) | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Levente Szabo | 2012-05-14 19:19 | End Date | 6/May/16 | 1/Jun/16
B4B-7 | Graphic designer briefing (1.) | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Levente Szabo | 2012-05-14 19:21 | Start Date | 1/Jun/16 | 3/Jun/16
B4B-7 | Graphic designer briefing (1.) | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Levente Szabo | 2012-05-14 19:21 | End Date | 1/Jun/16 | 3/Jun/16
B4B-7 | Graphic designer briefing (1.) | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Levente Szabo | 2012-05-14 19:29 | Link |  | This issue relates to B4B-8
B4B-7 | Graphic designer briefing (1.) | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Levente Szabo | 2012-05-14 19:37 | labels |  | UI&UX
B4B-7 | Graphic designer briefing (1.) | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Levente Szabo | 2012-05-17 13:25 | Sprint |  | BVP Sprint 2
B4B-7 | Graphic designer briefing (1.) | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Levente Szabo | 2012-05-18 16:24 | timeestimate |  | 0
B4B-7 | Graphic designer briefing (1.) | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Dalia Lens | 2012-05-18 16:24 | timespent |  | 5400
B4B-7 | Graphic designer briefing (1.) | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Dalia Lens | 2012-05-18 16:24 | WorklogId | 10201
B4B-7 | Graphic designer briefing (1.) | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Levente Szabo | 2012-05-18 17:59 | Link |  | This issue blocks B4B-8
B4B-7 | Graphic designer briefing (1.) | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Levente Szabo | 2012-05-18 17:59 | Link | This issue relates to B4B-8
B4B-7 | Graphic designer briefing (1.) | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Levente Szabo | 2012-05-22 14:41 | resolution |  | Done
B4B-7 | Graphic designer briefing (1.) | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Dalia Lens | 2012-05-22 14:41 | status | To Do | Done
B4B-7 | Graphic designer briefing (1.) | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Levente Szabo | 2012-07-14 14:21 | labels | UI&UX | user-experience user-interface
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-14 18:50 | Link |  | This issue is blocked by B4B-5
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-14 18:50 | labels |  | validation
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-14 19:18 | Link |  | This issue blocks B4B-7
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-14 19:20 | Start Date |  | 1/Jun/16
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-14 19:20 | End Date |  | 3/Jun/16
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-17 13:25 | Sprint |  | BVP Sprint 1
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-18 12:20 | Link |  | This issue relates to B4B-8
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-18 16:07 | timeestimate |  | 0
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-18 16:07 | timespent |  | 43200
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-18 16:07 | WorklogId | 10200
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-19 13:43 | status | To Do | In Progress
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-22 14:41 | resolution |  | Done
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-22 14:41 | status | In Progress | Done
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-08-09 11:41 | Story Points |  | 6
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-08-11 14:58 | labels | validation
B4B-6 | MVP functionality | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-08-11 15:02 | labels |  | validation
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 18:48 | Link |  | This issue relates to B4B-3
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 18:50 | Link |  | This issue blocks B4B-6
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 18:51 | labels |  | validation
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 19:23 | Start Date |  | 17/May/16
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 19:24 | End Date |  | 31/May/16
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-17 13:24 | Sprint |  | BVP Sprint 1
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-17 13:24 | Rank |  | Ranked higher
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-18 13:24 | status | To Do | In Progress
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-18 13:42 | priority | Medium | Low
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-18 13:43 | priority | Low | Lowest
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-18 14:44 | resolution |  | Done
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-18 14:44 | status | In Progress | Done
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-19 13:45 | resolution | Done
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-19 13:45 | status | Done | In Progress
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-22 15:01 | resolution |  | Done
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-22 15:01 | status | In Progress | Done
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-24 14:33 | timeestimate |  | 0
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-24 14:33 | timespent |  | 288000
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-24 14:33 | WorklogId | 10404
B4B-5 | Traditional market research | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-08-09 11:41 | Story Points |  | 22
B4B-4 | Validation landing page | Done | Done | 2012-05-14 18:44 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-14 18:44 | Link |  | This issue is blocked by B4B-3
B4B-4 | Validation landing page | Done | Done | 2012-05-14 18:44 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-14 19:22 | Start Date |  | 18/May/16
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-14 19:22 | End Date |  | 18/May/16
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-17 13:24 | Sprint |  | BVP Sprint 1
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-18 13:43 | priority | High | Highest
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-18 14:44 | status | To Do | In Progress
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-18 14:47 | resolution |  | Done
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-18 14:47 | status | In Progress | Done
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-18 17:59 | Link |  | This issue relates to B4B-8
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-22 14:36 | status | Done | Done
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-22 14:46 | resolution | Done
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-22 14:46 | status | Done | To Do
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-22 14:46 | resolution |  | Done
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-22 14:46 | status | To Do | Done
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-22 14:46 | resolution | Done
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-22 14:46 | status | Done | In Progress
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-23 10:19 | Fix Version |  | 1.0
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-23 13:01 | Story Points |  | 2
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-24 14:22 | resolution |  | Done
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-24 14:22 | status | In Progress | Done
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-24 14:22 | timeestimate |  | 0
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-24 14:22 | timespent |  | 28800
B4B-4 | Validation landing page | Done | Done | 2012-05-14 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-24 14:22 | WorklogId | 10405
B4B-3 | Customer interviews | Done | Done | 2012-05-14 18:40 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 18:41 | summary | Conduct 50 customer interviews | Customer interviews
B4B-3 | Customer interviews | Done | Done | 2012-05-14 18:40 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 18:44 | Link |  | This issue blocks B4B-4
B4B-3 | Customer interviews | Done | Done | 2012-05-14 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 18:45 | labels |  | validation
B4B-3 | Customer interviews | Done | Done | 2012-05-14 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 18:48 | Link |  | This issue relates to B4B-5
B4B-3 | Customer interviews | Done | Done | 2012-05-14 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 18:57 | assignee |  | Owen Klyed
B4B-3 | Customer interviews | Done | Done | 2012-05-14 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 19:01 | Start Date |  | 17/May/16
B4B-3 | Customer interviews | Done | Done | 2012-05-14 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 19:02 | End Date |  | 31/May/16
B4B-3 | Customer interviews | Done | Done | 2012-05-14 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 19:24 | Story Points |  | 72
B4B-3 | Customer interviews | Done | Done | 2012-05-14 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 22:14 | timeestimate |  | 0
B4B-3 | Customer interviews | Done | Done | 2012-05-14 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 22:14 | timespent |  | 14400
B4B-3 | Customer interviews | Done | Done | 2012-05-14 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 22:14 | WorklogId | 10100
B4B-3 | Customer interviews | Done | Done | 2012-05-14 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-17 13:24 | Sprint |  | BVP Sprint 1
B4B-3 | Customer interviews | Done | Done | 2012-05-14 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-18 13:24 | status | To Do | In Progress
B4B-3 | Customer interviews | Done | Done | 2012-05-14 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-19 16:04 | resolution |  | Done
B4B-3 | Customer interviews | Done | Done | 2012-05-14 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-19 16:04 | status | In Progress | Done
B4B-1 | Secure and buy the domain name | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-11 11:55 | description |  | We need to make sure that we have the domain name rights and all social media accounts.
B4B-1 | Secure and buy the domain name | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-11 11:55 | priority | Medium | High
B4B-1 | Secure and buy the domain name | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-11 11:55 | Sprint |  | LS Sprint 1
B4B-1 | Secure and buy the domain name | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-11 11:55 | labels |  | web
B4B-1 | Secure and buy the domain name | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-11 12:53 | Story Points |  | 4
B4B-1 | Secure and buy the domain name | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-14 18:52 | Sprint | LS Sprint 1
B4B-1 | Secure and buy the domain name | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-14 18:57 | assignee |  | Dalia Lens
B4B-1 | Secure and buy the domain name | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-14 19:05 | Start Date |  | 17/May/16
B4B-1 | Secure and buy the domain name | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-14 19:06 | End Date |  | 17/May/16
B4B-1 | Secure and buy the domain name | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-17 13:28 | Sprint |  | Dev sprint
B4B-1 | Secure and buy the domain name | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-17 13:28 | Rank |  | Ranked lower
B4B-1 | Secure and buy the domain name | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-17 13:28 | Rank |  | Ranked higher
B4B-1 | Secure and buy the domain name | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-18 13:48 | priority | High | Low
B4B-1 | Secure and buy the domain name | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-22 14:45 | resolution |  | Done
B4B-1 | Secure and buy the domain name | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-22 14:45 | status | To Do | Done
490