## Issue Navigator
Key | T | Summary | P | Status | Flagged | Assignee | Time spent | Created | Updated | Labels | Story points | Components | Watchers | Sprint
B4B-26 | Story | Set up Hootsuite account | Medium | In Progress | Impediment | Casey Ford | 16.8 | 2012-09-15 | 2012-12-15 11:25 | CRM, marketing | 24 | Landing Page, website design | 1 | Marketing and customer rel
B4B-29 | Task | Plan the email campaigns | Medium | In Progress |  | Levente Szabo | 40 | 2012-09-18 | 2012-12-05 11:08 | CRM, marketing | 22 | Landing Page, website design | 4 | Marketing and customer rel
B4B-28 | Sub-task | Copy for email campaigns | Low | In Progress |  | Casey Ford | 32.4 | 2012-09-16 | 2012-12-05 11:07 | CRM, marketing | 24 | Android App, iOS App | 6 | Marketing and customer rel
B4B-30 | Task | Set up FB group for beta testers | Medium | To Do |  | Casey Ford |  | 2012-09-18 | 2012-09-18 15:38 | CRM, marketing | 8 | Landing Page, website design | 2 | Marketing and customer rel
B4B-27 | Story | Set up Mailchimp | Low | To Do |  | Casey Ford |  | 2012-09-18 | 2012-12-06 14:56 | CRM, marketing | 6 | Android App, iOS App | 4 | Marketing and customer rel
B4B-24 | Sub-task | Video feed | Medium | Done |  | Dalia Lens | 80 | 2012-09-20 | 2012-12-05 11:43 | DEV, IT | 8 | Landing Page, website design | 3 | Dev sprint
B4B-23 | Sub-task | Video sharing feature | Low | In Progress |  | Robert Mongose | 21.6 | 2012-09-18 | 2012-12-05 11:24 | DEV, IT | 6 | Landing Page, website design | 6 | Dev sprint
B4B-22 | Sub-task | Video recording feature | Medium | In Progress |  | Robert Mongose | 16 | 2012-09-18 | 2012-12-05 11:13 | DEV, IT | 4 | Android App, iOS App | 5 | Dev sprint
B4B-21 | Epic | Implement MVP functions | Medium | In Progress | Impediment | Levente Szabo | 40.9 | 2012-09-18 | 2012-12-05 11:12 | DEV, IT | 4 | Landing Page, website design | 3 | Dev sprint
B4B-20 | Sub-task | Log-in form | Medium | In Progress |  | Robert Mongose | 32 | 2012-05-19 | 2012-12-06 14:47 | DEV, IT | 22 | Android App, iOS App | 4 | Dev sprint
B4B-19 | Sub-task | Sign-up form | Medium | In Progress |  | Levente Szabo | 2.42 | 2012-05-19 | 2012-12-05 11:15 | DEV, IT | 30 | Landing Page, website design | 5 | Dev sprint
B4B-25 | Sub-task | "React" feature | Medium | To Do |  | Dalia Lens |  | 2012-05-24 | 2012-12-06 14:45 | DEV, IT | 40 | Android App, iOS App | 2 | Dev sprint
B4B-16 | Task | Set up Dev Environment | Medium | To Do |  | Robert Mongose |  | 2012-05-19 | 2012-12-05 11:19 | DEV, IT | 40 | Android App, iOS App | 3 | Dev sprint
B4B-18 | Sub-task | Tutorial section | Medium | In Progress |  | Dalia Lens | 21 | 2012-05-17 | 2012-12-06 14:21 | DEV, IT | 6 | Landing Page, website design | 4 | Dev sprint
B4B-17 | Task | Set up cloud hosting | Low | In Progress | Impediment | Robert Mongose | 16 | 2012-05-17 | 2012-12-06 14:58 | DEV, IT | 8 | Android App, iOS App | 2 | Dev sprint
B4B-15 | Task | Set up DB | Medium | In Progress |  | Robert Mongose | 40 | 2012-05-17 | 2012-07-14 14:19 | DEV, IT | 2 | Landing Page, website design | 4 | Dev sprint
B4B-11 | Task | Landing page copy | Medium | In Progress |  | Dalia Lens | 32 | 2012-05-11 | 2012-12-15 15:15 | billable, web | 6 | Android App, iOS App | 1 | Landing page sprint
B4B-49 | Task | Beem Inc. - Company website design | Highest | Done |  | Dalia Lens | 2.42 | 2012-05-17 | 2012-12-05 11:02 | billable | 8 | Landing Page, website design | 4
B4B-8 | Task | Design Feedback (1.) | Medium | Done | Impediment | Dalia Lens | 3 | 2012-05-17 | 2012-12-05 11:01 | interactions | 4 | Landing Page, website design | 3 | UX&UI sprint
B4B-10 | Task | Design Feedback (3.) | Medium | To Do |  | Dalia Lens |  | 2012-05-17 | 2012-12-06 14:16 | user-experience, user-interface | 4 |  | 1 | UX&UI sprint
B4B-9 | Task | Design Feedback (2.) | Medium | Done |  | Dalia Lens | 32 | 2012-05-16 | 2012-12-05 11:32 | user-experience, user-interface | 4 |  | 2 | UX&UI sprint
B4B-7 | Task | Graphic designer briefing (1.) | High | Done |  | Dalia Lens | 16 | 2012-05-16 | 2012-12-05 11:32 | user-experience, user-interface | 4 |  | 1 | UX&UI sprint
B4B-4 | Task | Validation landing page | Highest | Done |  | Owen Klyed | 40 | 2012-05-16 | 2012-12-05 11:40 | validation | 14 | Landing Page, website design | 4 | BVP Validation Sprint
B4B-3 | Task | Customer interviews | Highest | Done |  | Owen Klyed | 32 | 2012-05-16 | 2012-08-09 11:39 | validation | 18 | Landing Page, website design | 1 | BVP Validation Sprint
B4B-5 | Task | Traditional market research | Lowest | Done |  | Owen Klyed | 2.42 | 2012-05-16 | 2012-12-06 14:39 | validation | 8 | Landing Page, website design | 2 | BVP Validation Sprint
B4B-6 | Task | MVP functionality | High | Done |  | Owen Klyed | 3 | 2012-09-18 | 2012-12-06 14:22 | validation | 4 | Landing Page, website design | 1 | BVP Validation Sprint
B4B-1 | Task | Secure and buy the domain name | Low | Done | Impediment | Dalia Lens | 21.8 | 2012-09-18 | 2012-12-05 11:29 | web | 6 |  | 4 | Dev sprint
B4B-13 | Task | Decision on landing page design | Medium | In Progress |  | Dalia Lens |  | 2012-09-18 | 2012-12-05 11:25 | web | 6 | Landing Page | 5 | Landing page sprint
B4B-12 | Task | A/B test landing page | Low | In Progress |  | Dalia Lens | 82.76 | 2012-09-18 | 2012-12-06 14:51 | web | 8 | Android App, iOS App | 4 | Landing page sprint
B4B-14 | Task | Create landing page | Medium | To Do |  | Dalia Lens | 93.75 | 2012-09-18 | 2012-12-06 14:48 | validation | 6 |  | 3 | Landing page sprint
B4B-32 | Sub-task | Feedback on overall design approach | Medium | Done |  | Owen Klyed |  | 2012-09-18 | 2012-12-05 11:38 | web | 2 | Android App, iOS App | 4 | UX&UI sprint
B4B-31 | Task | Collect feedback | Low | To Do |  | Casey Ford |  | 2012-09-18 | 2012-12-05 11:22 | validation | 4 |  | 1 | Marketing and customer rel
B4B-34 | Sub-task | Clarify color schemes | Medium | In Progress |  | Casey Ford | 2 | 2012-09-18 | 2012-12-05 11:13 | web | 6 | Android App, iOS App, Landing Page | 2 | UX&UI sprint
B4B-33 | Sub-task | Feedback on components | Medium | To Do |  | Dalia Lens | 74.92 | 2012-09-18 | 2012-12-06 14:43 | web | 22 |  | 1 | UX&UI sprint
B4B-55 | Sub-task | Brand color scheme | Medium | To Do |  |  | 4.9 | 2012-09-18 | 2012-12-12 17:10 | web | 2 |  | 1
B4B-58 | Sub-task | Website layout | Medium | To Do |  |  | 120.9 | 2012-09-18 | 2012-12-05 11:23 | web | 72 |  | 1
B4B-57 | Sub-task | Second mockup | Medium | To Do |  |  |  | 2012-09-18 | 2012-05-22 14:45 | web | 4 |  | 1
B4B-56 | Sub-task | First mockup | Medium | To Do |  |  |  | 2012-09-18 |  | web | 6
B4B-36 | Sub-task | Phone interviews | Medium | To Do |  | Owen Klyed |  | 2012-09-18 |  | validation | 6 |  |  | BVP Validation Sprint
B4B-35 | Sub-task | In person interviews | Medium | To Do |  | Owen Klyed |  | 2012-09-18 |  | validation | 6 |  |  | BVP Validation Sprint
B4B-38 | Sub-task | Historical analysis | Low | To Do |  | Dalia Lens |  | 2012-09-18 |  | validation | 6 |  |  | BVP Validation Sprint
B4B-37 | Sub-task | Online research | Low | To Do |  | Owen Klyed |  | 2012-09-18 |  | validation | 6 |  |  | BVP Validation Sprint
42 | [10 empty] | 496 |  | 105