## Test Run Status per Execution
Executions | Column Labels
Row Labels | PASS | TODO | EXECUTING | FAIL | ABORTED | Grand Total
[EBANK-45] Security and compliance testing - Mobile/web browser |  | 1 |  |  |  | 1
[EBANK-51] Planned testing for PSD2 | 2 |  |  | 2 | 2 | 6
[EBANK-46] E-Bank Mobile app v1.1 | 1 | 2 | 3 |  | 1 | 7
[EBANK-47] E-Bank Mobile app v1.2 | 1 |  | 2 | 1 | 3 | 7
[EBANK-44] Security and compliance testing - iOS | 3 | 2 | 1 | 1 |  | 7
[EBANK-43] Security and compliance testing - Android | 2 | 4 |  |  | 1 | 7
[EBANK-49] Web elements on mobile browser | 6 | 4 | 3 | 3 | 1 | 17
[EBANK-50] Mobile web elements | 5 | 4 | 3 | 3 | 2 | 17
Grand Total | 20 | 17 | 12 | 10 | 10 | 69

## Defects per Execution
Executions | Defects
[EBANK-47] E-Bank Mobile app v1.2 | 0
[EBANK-45] Security and compliance testing - Mobile/web browser | 0
[EBANK-46] E-Bank Mobile app v1.1 | 1
[EBANK-51] Planned testing for PSD2 | 1
[EBANK-43] Security and compliance testing - Android | 1
[EBANK-49] Web elements on mobile browser | 2
[EBANK-44] Security and compliance testing - iOS | 2
[EBANK-50] Mobile web elements | 3
Grand Total | 10

## Test Run Status per Version
Fix versions | Column Labels
Row Labels | PASS | TODO | EXECUTING | FAIL | ABORTED | Grand Total
1.1.0 | 1 | 1 |  |  |  | 2
1.3.0 | 3 | 2 | 2 | 2 |  | 9
1.2.0 | 5 | 3 | 2 | 2 |  | 12
1.4.0-rc | 6 | 4 | 6 | 1 | 1 | 18
1.5.0-beta | 5 | 7 | 2 | 5 | 9 | 28
Grand Total | 20 | 17 | 12 | 10 | 10 | 69

## Defects per Version
Fix Versions | Defects
1.5.0-beta | 28
1.4.0-rc | 18
1.2.0 | 12
1.3.0 | 9
1.1.0 | 2
Grand Total | 69

## Test Run Status per Environment
Enivronments | Column Labels
Row Labels | PASS | TODO | EXECUTING | FAIL | ABORTED | Grand Total
Chrome, Firefox |  | 1 |  |  |  | 1
WebClient, Windows | 2 |  |  | 2 | 2 | 6
Chrome, Linux, Windows | 1 |  | 2 | 1 | 3 | 7
iOS11, iOS12 | 3 | 2 | 1 | 1 |  | 7
Android | 2 | 4 |  |  | 1 | 7
Mobile, Safari | 2 | 3 | 1 | 3 | 2 | 11
Android9.0, iOS11, iOS12 | 4 | 3 | 5 |  | 1 | 13
Chrome, Mobile | 6 | 4 | 3 | 3 | 1 | 17
Grand Total | 20 | 17 | 12 | 10 | 10 | 69

## Defects per Environment
Environments | Defects
Chrome, Firefox | 1
WebClient, Windows | 6
Chrome, Linux, Windows | 7
iOS11, iOS12 | 7
Android | 7
Mobile, Safari | 11
Android9.0, iOS11, iOS12 | 13
Chrome, Mobile | 17
Grand Total | 69

## Test Run Status per Assignee
Assignees | Column Labels
Row Labels | PASS | TODO | EXECUTING | FAIL | ABORTED | Grand Total
Bob Mitchell | 3 | 1 | 1 | 2 |  | 7
Casey Ford | 3 | 2 | 1 |  | 3 | 9
Dalia Lens | 7 | 5 | 2 |  |  | 14
Zoe Barnes | 2 | 4 | 2 | 3 | 5 | 16
Robert Mongose | 5 | 5 | 6 | 5 | 2 | 23
Grand Total | 20 | 17 | 12 | 10 | 10 | 69

## Defects per Assignee
Assignees | Defects
Bob Mitchell | 7
Casey Ford | 9
Dalia Lens | 14
Zoe Barnes | 16
Robert Mongose | 23
Grand Total | 69

## Test Runs
Test Key | Test Summary | Test | Test Type | Test Execution Key | Test Execution Summary | Test Execution | Test Run Fix Versions | Test Run Test Environments | Test Run Assignee | Test Run Executed By | Test Run Duration | Test Run Defects | Test Run Defects Count | Test Run Status
EBANK-42 | TPP list can be accessed by Bank employees | [EBANK-42] TPP list can be accessed by Bank employees | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.1.0 | Chrome, Mobile | Robert Mongose |  | 16.32 |  | 0 | PASS
EBANK-42 | TPP list can be accessed by Bank employees | [EBANK-42] TPP list can be accessed by Bank employees | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.1.0 | Mobile, Safari | Robert Mongose |  |  |  | 0 | TODO
EBANK-42 | TPP list can be accessed by Bank employees | [EBANK-42] TPP list can be accessed by Bank employees | Manual | EBANK-51 | Planned testing for PSD2 | [EBANK-51] Planned testing for PSD2 | 1.5.0-beta | WebClient, Windows | Robert Mongose |  |  |  | 0 | FAIL
EBANK-41 | New third-party request can be registered on Bank's API platform | [EBANK-41] New third-party request can be registered on Bank's API platform | Manual | EBANK-51 | Planned testing for PSD2 | [EBANK-51] Planned testing for PSD2 | 1.5.0-beta | WebClient, Windows | Robert Mongose |  |  |  | 0 | FAIL
EBANK-40 | Payment verifications performed for account balance | [EBANK-40] Payment verifications performed for account balance | Manual | EBANK-51 | Planned testing for PSD2 | [EBANK-51] Planned testing for PSD2 | 1.5.0-beta | WebClient, Windows | Robert Mongose |  |  |  | 0 | ABORTED
EBANK-31 | Onboarding instructions depend on customer account type (Standard) | [EBANK-31] Onboarding instructions depend on customer account type (Standard) | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.5.0-beta | Chrome, Mobile | Robert Mongose |  |  |  | 0 | TODO
EBANK-31 | Onboarding instructions depend on customer account type (Standard) | [EBANK-31] Onboarding instructions depend on customer account type (Standard) | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.5.0-beta | Mobile, Safari | Robert Mongose |  | 112.43 | EBANK-56 EBANK-58 | 1 | ABORTED
EBANK-26 | HTTP protocol used to store cookies | [EBANK-26] HTTP protocol used to store cookies | Manual | EBANK-46 | E-Bank Mobile app v1.1 | [EBANK-46] E-Bank Mobile app v1.1 | 1.5.0-beta | Android9.0, iOS11, iOS12 | Casey Ford |  |  |  | 0 | ABORTED
EBANK-26 | HTTP protocol used to store cookies | [EBANK-26] HTTP protocol used to store cookies | Manual | EBANK-47 | E-Bank Mobile app v1.2 | [EBANK-47] E-Bank Mobile app v1.2 | 1.5.0-beta | Chrome, Linux, Windows | Casey Ford |  |  |  | 0 | ABORTED
EBANK-26 | HTTP protocol used to store cookies | [EBANK-26] HTTP protocol used to store cookies | Manual | EBANK-43 | Security and compliance testing - Android | [EBANK-43] Security and compliance testing - Android | 1.5.0-beta | Android | Casey Ford |  |  |  | 0 | ABORTED
EBANK-26 | HTTP protocol used to store cookies | [EBANK-26] HTTP protocol used to store cookies | Manual | EBANK-44 | Security and compliance testing - iOS | [EBANK-44] Security and compliance testing - iOS | 1.5.0-beta | iOS11, iOS12 | Casey Ford |  |  | EBANK-60 EBANK-61 | 1 | TODO
EBANK-25 | Database consistency test | [EBANK-25] Database consistency test | Manual | EBANK-46 | E-Bank Mobile app v1.1 | [EBANK-46] E-Bank Mobile app v1.1 | 1.5.0-beta | Android9.0, iOS11, iOS12 | Casey Ford |  |  |  | 0 | EXECUTING
EBANK-25 | Database consistency test | [EBANK-25] Database consistency test | Manual | EBANK-47 | E-Bank Mobile app v1.2 | [EBANK-47] E-Bank Mobile app v1.2 | 1.5.0-beta | Chrome, Linux, Windows | Casey Ford |  |  |  | 0 | PASS
EBANK-25 | Database consistency test | [EBANK-25] Database consistency test | Manual | EBANK-43 | Security and compliance testing - Android | [EBANK-43] Security and compliance testing - Android | 1.5.0-beta | Android | Casey Ford |  |  |  | 0 | TODO
EBANK-25 | Database consistency test | [EBANK-25] Database consistency test | Manual | EBANK-44 | Security and compliance testing - iOS | [EBANK-44] Security and compliance testing - iOS | 1.5.0-beta | iOS11, iOS12 | Casey Ford |  |  |  | 0 | PASS
EBANK-24 | Verify required SSL security compliance | [EBANK-24] Verify required SSL security compliance | Manual | EBANK-46 | E-Bank Mobile app v1.1 | [EBANK-46] E-Bank Mobile app v1.1 | 1.5.0-beta | Android9.0, iOS11, iOS12 | Casey Ford |  | 64 | EBANK-65 EBANK-59 | 1 | PASS
EBANK-24 | Verify required SSL security compliance | [EBANK-24] Verify required SSL security compliance | Manual | EBANK-47 | E-Bank Mobile app v1.2 | [EBANK-47] E-Bank Mobile app v1.2 | 1.5.0-beta | Chrome, Linux, Windows | Zoe Barnes |  |  |  | 0 | EXECUTING
EBANK-24 | Verify required SSL security compliance | [EBANK-24] Verify required SSL security compliance | Manual | EBANK-43 | Security and compliance testing - Android | [EBANK-43] Security and compliance testing - Android | 1.5.0-beta | Android | Zoe Barnes |  |  |  | 0 | TODO
EBANK-24 | Verify required SSL security compliance | [EBANK-24] Verify required SSL security compliance | Manual | EBANK-44 | Security and compliance testing - iOS | [EBANK-44] Security and compliance testing - iOS | 1.5.0-beta | iOS11, iOS12 | Zoe Barnes |  |  |  | 0 | PASS
EBANK-23 | Response time test at different connection speeds | [EBANK-23] Response time test at different connection speeds | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.5.0-beta | Chrome, Mobile | Zoe Barnes |  | 96 |  | 0 | ABORTED
EBANK-23 | Response time test at different connection speeds | [EBANK-23] Response time test at different connection speeds | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.5.0-beta | Mobile, Safari | Zoe Barnes |  |  |  | 0 | ABORTED
EBANK-22 | Desktop Operating System compatibility test | [EBANK-22] Desktop Operating System compatibility test | Manual | EBANK-46 | E-Bank Mobile app v1.1 | [EBANK-46] E-Bank Mobile app v1.1 | 1.5.0-beta | Android9.0, iOS11, iOS12 | Zoe Barnes |  |  |  | 0 | TODO
EBANK-22 | Desktop Operating System compatibility test | [EBANK-22] Desktop Operating System compatibility test | Manual | EBANK-47 | E-Bank Mobile app v1.2 | [EBANK-47] E-Bank Mobile app v1.2 | 1.5.0-beta | Chrome, Linux, Windows | Zoe Barnes |  |  |  | 0 | ABORTED
EBANK-22 | Desktop Operating System compatibility test | [EBANK-22] Desktop Operating System compatibility test | Manual | EBANK-43 | Security and compliance testing - Android | [EBANK-43] Security and compliance testing - Android | 1.2.0 | Android | Zoe Barnes |  |  |  | 0 | PASS
EBANK-22 | Desktop Operating System compatibility test | [EBANK-22] Desktop Operating System compatibility test | Manual | EBANK-44 | Security and compliance testing - iOS | [EBANK-44] Security and compliance testing - iOS | 1.2.0 | iOS11, iOS12 | Zoe Barnes |  |  | EBANK-60 EBANK-61 | 1 | EXECUTING
EBANK-20 | Mobile browser compatibility test | [EBANK-20] Mobile browser compatibility test | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.2.0 | Chrome, Mobile | Robert Mongose |  |  |  | 0 | EXECUTING
EBANK-20 | Mobile browser compatibility test | [EBANK-20] Mobile browser compatibility test | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.2.0 | Mobile, Safari | Robert Mongose |  |  |  | 0 | PASS
EBANK-18 | Loading website with various connections quality | [EBANK-18] Loading website with various connections quality | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.2.0 | Chrome, Mobile | Robert Mongose |  |  |  | 0 | PASS
EBANK-18 | Loading website with various connections quality | [EBANK-18] Loading website with various connections quality | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.2.0 | Mobile, Safari | Robert Mongose |  |  |  | 0 | PASS
EBANK-17 | Keyboard switching is automatic for number type fields on mobile | [EBANK-17] Keyboard switching is automatic for number type fields on mobile | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.2.0 | Chrome, Mobile | Robert Mongose |  |  | EBANK-60 EBANK-61 | 1 | PASS
EBANK-17 | Keyboard switching is automatic for number type fields on mobile | [EBANK-17] Keyboard switching is automatic for number type fields on mobile | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.2.0 | Mobile, Safari | Robert Mongose |  |  |  | 0 | TODO
EBANK-16 | Irrelevant menu items don't appear | [EBANK-16] Irrelevant menu items don't appear | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.2.0 | Chrome, Mobile | Zoe Barnes |  |  |  | 0 | TODO
EBANK-16 | Irrelevant menu items don't appear | [EBANK-16] Irrelevant menu items don't appear | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.2.0 | Mobile, Safari | Zoe Barnes |  |  |  | 0 | TODO
EBANK-15 | All documented shortcut keys can be used | [EBANK-15] All documented shortcut keys can be used | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.2.0 | Chrome, Mobile | Zoe Barnes |  |  |  | 0 | FAIL
EBANK-15 | All documented shortcut keys can be used | [EBANK-15] All documented shortcut keys can be used | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.2.0 | Mobile, Safari | Zoe Barnes |  |  |  | 0 | FAIL
EBANK-14 | Insufficient funds notifications are straightforward | [EBANK-14] Insufficient funds notifications are straightforward | Manual | EBANK-51 | Planned testing for PSD2 | [EBANK-51] Planned testing for PSD2 | 1.5.0-beta | WebClient, Windows | Zoe Barnes |  |  |  | 0 | ABORTED
EBANK-13 | Table scrolling edge cases are handled | [EBANK-13] Table scrolling edge cases are handled | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.4.0-rc | Chrome, Mobile | Zoe Barnes |  |  |  | 0 | FAIL
EBANK-13 | Table scrolling edge cases are handled | [EBANK-13] Table scrolling edge cases are handled | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.5.0-beta | Mobile, Safari | Robert Mongose |  | 64 | EBANK-60 EBANK-61 | 1 | FAIL
EBANK-12 | Type ahead feature is default for form filling | [EBANK-12] Type ahead feature is default for form filling | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.5.0-beta | Chrome, Mobile | Robert Mongose |  |  |  | 0 | FAIL
EBANK-12 | Type ahead feature is default for form filling | [EBANK-12] Type ahead feature is default for form filling | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.5.0-beta | Mobile, Safari | Robert Mongose |  |  |  | 0 | FAIL
EBANK-11 | Confirmations are prompted when leaving forms without saving | [EBANK-11] Confirmations are prompted when leaving forms without saving | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.5.0-beta | Chrome, Mobile | Robert Mongose |  |  |  | 0 | TODO
EBANK-11 | Confirmations are prompted when leaving forms without saving | [EBANK-11] Confirmations are prompted when leaving forms without saving | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.4.0-rc | Android9.0, iOS11, iOS12 | Robert Mongose |  |  |  | 0 | EXECUTING
EBANK-10 | Abbreviations are consistently used | [EBANK-10] Abbreviations are consistently used | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.4.0-rc | Chrome, Mobile | Robert Mongose |  |  |  | 0 | EXECUTING
EBANK-10 | Abbreviations are consistently used | [EBANK-10] Abbreviations are consistently used | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.4.0-rc | Mobile, Safari | Robert Mongose |  |  |  | 0 | EXECUTING
EBANK-9 | Language is automatically selected based on device location | [EBANK-9] Language is automatically selected based on device location | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.4.0-rc | Chrome, Mobile | Robert Mongose |  |  | EBANK-56 EBANK-58 | 1 | EXECUTING
EBANK-9 | Language is automatically selected based on device location | [EBANK-9] Language is automatically selected based on device location | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.4.0-rc | Android9.0, iOS11, iOS12 | Robert Mongose |  |  |  | 0 | EXECUTING
EBANK-8 | Payment transaction submitted multiple times | [EBANK-8] Payment transaction submitted multiple times | Manual | EBANK-46 | E-Bank Mobile app v1.1 | [EBANK-46] E-Bank Mobile app v1.1 | 1.4.0-rc | Android9.0, iOS11, iOS12 | Dalia Lens |  |  |  | 0 | EXECUTING
EBANK-8 | Payment transaction submitted multiple times | [EBANK-8] Payment transaction submitted multiple times | Manual | EBANK-47 | E-Bank Mobile app v1.2 | [EBANK-47] E-Bank Mobile app v1.2 | 1.4.0-rc | Chrome, Linux, Windows | Zoe Barnes |  |  |  | 0 | ABORTED
EBANK-8 | Payment transaction submitted multiple times | [EBANK-8] Payment transaction submitted multiple times | Manual | EBANK-45 | Security and compliance testing - Mobile/web browser | [EBANK-45] Security and compliance testing - Mobile/web browser | 1.4.0-rc | Chrome, Firefox | Robert Mongose |  |  |  | 0 | TODO
EBANK-8 | Payment transaction submitted multiple times | [EBANK-8] Payment transaction submitted multiple times | Manual | EBANK-43 | Security and compliance testing - Android | [EBANK-43] Security and compliance testing - Android | 1.4.0-rc | Android | Dalia Lens |  | 24 | EBANK-69 EBANK-61 | 1 | TODO
EBANK-8 | Payment transaction submitted multiple times | [EBANK-8] Payment transaction submitted multiple times | Manual | EBANK-44 | Security and compliance testing - iOS | [EBANK-44] Security and compliance testing - iOS | 1.4.0-rc | iOS11, iOS12 | Dalia Lens |  |  |  | 0 | TODO
EBANK-7 | Financial goal progress bar visibility on different screens | [EBANK-7] Financial goal progress bar visibility on different screens | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.4.0-rc | Chrome, Mobile | Dalia Lens |  |  |  | 0 | TODO
EBANK-7 | Financial goal progress bar visibility on different screens | [EBANK-7] Financial goal progress bar visibility on different screens | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.4.0-rc | Android9.0, iOS11, iOS12 | Dalia Lens |  |  |  | 0 | PASS
EBANK-7 | Financial goal progress bar visibility on different screens | [EBANK-7] Financial goal progress bar visibility on different screens | Manual | EBANK-51 | Planned testing for PSD2 | [EBANK-51] Planned testing for PSD2 | 1.4.0-rc | WebClient, Windows | Dalia Lens |  | 48.32 | EBANK-62 EBANK-63 EBANK-64 | 1 | PASS
EBANK-6 | Onboarding instructions depend on customer account type (Premium) | [EBANK-6] Onboarding instructions depend on customer account type (Premium) | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.4.0-rc | Chrome, Mobile | Dalia Lens |  |  |  | 0 | PASS
EBANK-6 | Onboarding instructions depend on customer account type (Premium) | [EBANK-6] Onboarding instructions depend on customer account type (Premium) | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.4.0-rc | Android9.0, iOS11, iOS12 | Dalia Lens |  |  |  | 0 | PASS
EBANK-5 | Behavior of form instructions | [EBANK-5] Behavior of form instructions | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.4.0-rc | Chrome, Mobile | Dalia Lens |  |  |  | 0 | PASS
EBANK-5 | Behavior of form instructions | [EBANK-5] Behavior of form instructions | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.4.0-rc | Android9.0, iOS11, iOS12 | Dalia Lens |  | 40.21 | EBANK-66 | 1 | PASS
EBANK-4 | Use various text field widths | [EBANK-4] Use various text field widths | Manual | EBANK-49 | Web elements on mobile browser | [EBANK-49] Web elements on mobile browser | 1.5.0-beta | Chrome, Mobile | Dalia Lens |  |  |  | 0 | PASS
EBANK-4 | Use various text field widths | [EBANK-4] Use various text field widths | Manual | EBANK-50 | Mobile web elements | [EBANK-50] Mobile web elements | 1.5.0-beta | Android9.0, iOS11, iOS12 | Dalia Lens |  |  |  | 0 | TODO
EBANK-3 | Enter different data types | [EBANK-3] Enter different data types | Manual | EBANK-46 | E-Bank Mobile app v1.1 | [EBANK-46] E-Bank Mobile app v1.1 | 1.3.0 | Android9.0, iOS11, iOS12 | Dalia Lens |  |  |  | 0 | TODO
EBANK-3 | Enter different data types | [EBANK-3] Enter different data types | Manual | EBANK-47 | E-Bank Mobile app v1.2 | [EBANK-47] E-Bank Mobile app v1.2 | 1.3.0 | Chrome, Linux, Windows | Dalia Lens |  |  |  | 0 | EXECUTING
EBANK-3 | Enter different data types | [EBANK-3] Enter different data types | Manual | EBANK-43 | Security and compliance testing - Android | [EBANK-43] Security and compliance testing - Android | 1.3.0 | Android | Bob Mitchell |  |  |  | 0 | TODO
EBANK-3 | Enter different data types | [EBANK-3] Enter different data types | Manual | EBANK-44 | Security and compliance testing - iOS | [EBANK-44] Security and compliance testing - iOS | 1.3.0 | iOS11, iOS12 | Bob Mitchell |  | 136.23 |  | 0 | FAIL
EBANK-2 | Test the behavior of required fields for a card-not-present payment transaction | [EBANK-2] Test the behavior of required fields for a card-not-present payment transaction | Manual | EBANK-46 | E-Bank Mobile app v1.1 | [EBANK-46] E-Bank Mobile app v1.1 | 1.3.0 | Android9.0, iOS11, iOS12 | Bob Mitchell |  |  |  | 0 | EXECUTING
EBANK-2 | Test the behavior of required fields for a card-not-present payment transaction | [EBANK-2] Test the behavior of required fields for a card-not-present payment transaction | Manual | EBANK-47 | E-Bank Mobile app v1.2 | [EBANK-47] E-Bank Mobile app v1.2 | 1.3.0 | Chrome, Linux, Windows | Bob Mitchell |  |  |  | 0 | FAIL
EBANK-2 | Test the behavior of required fields for a card-not-present payment transaction | [EBANK-2] Test the behavior of required fields for a card-not-present payment transaction | Manual | EBANK-43 | Security and compliance testing - Android | [EBANK-43] Security and compliance testing - Android | 1.3.0 | Android | Bob Mitchell |  |  |  | 0 | PASS
EBANK-2 | Test the behavior of required fields for a card-not-present payment transaction | [EBANK-2] Test the behavior of required fields for a card-not-present payment transaction | Manual | EBANK-44 | Security and compliance testing - iOS | [EBANK-44] Security and compliance testing - iOS | 1.3.0 | iOS11, iOS12 | Bob Mitchell |  |  |  | 0 | PASS
EBANK-1 | Payment request is authenticated securely | [EBANK-1] Payment request is authenticated securely | Manual | EBANK-51 | Planned testing for PSD2 | [EBANK-51] Planned testing for PSD2 | 1.3.0 | WebClient, Windows | Bob Mitchell |  |  |  | 0 | PASS