## Versions
Project | Key | Version Name | Version Status | Version Progress - To Do | Version Progress - In Progress | Version Progress - Done | Version Progress - Unmapped | Version Start Date | Version Release Date | Version Description
Action Cam | ACTIONCAM | 0.1-internal | Unreleased | 3 | 0 | 15 | 0 | 2019-02-26 |  | Proof of Concept
|  | 0.2-internal | Unreleased | 6 | 1 | 17 | 0 | 2019-05-05 |  | Service runs locally
|  | 0.3-internal | Unreleased | 0 | 0 | 13 | 0 | 2019-06-19
|  | 0.4-internal | Unreleased | 0 | 2 | 12 | 0 | 2019-08-12
|  | 0.5-alpha | Archived | 0 | 0 | 15 | 0 | 2019-10-01 | 2019-11-01 | Alpha version, Android app only
|  | 0.5.1-alpha | Archived | 7 | 0 | 11 | 0 | 2019-11-05 | 2019-11-10 | Fixed infinite loading
|  | 0.5.2-alpha | Archived | 0 | 9 | 10 | 0 | 2019-11-13 | 2019-11-16 | More stable connection
|  | 0.6-beta | Archived | 0 | 4 | 12 | 0 | 2020-03-10 | 2020-04-13 | Beta version, Android app only
|  | 0.7-beta | Archived | 4 | 0 | 15 | 0 | 2020-04-20 | 2020-06-12 | Beta version with both Android and iOS apps
|  | 1.0.0 | Released | 5 | 2 | 26 | 0 | 2020-07-03 | 2020-09-14 | Public release
|  | 1.5.0 | Released | 0 | 4 | 13 | 0 | 2020-09-17 | 2020-10-05
|  | 2.0.0 | Released | 5 | 1 | 15 | 0 | 2020-10-13 | 2020-11-09 | Major release: 2.0.0
AirPortal | AIR | 0.1-local | Unreleased | 5 | 6 | 30 | 0 | 2018-08-06
|  | 0.2-alpha | Released | 0 | 0 | 3 | 0 | 2018-11-22 | 2018-11-30
|  | 0.5-beta | Released | 0 | 3 | 8 | 0 | 2018-12-02 | 2019-04-27
|  | 0.8-beta2 | Released | 4 | 13 | 35 | 0 | 2019-05-01 | 2019-09-10
|  | 1.0.0 | Released | 5 | 7 | 18 | 0 | 2019-09-13 | 2020-03-07 | Public release
AutoMotive | AUT | 0.1-poc | Unreleased | 9 | 0 | 23 | 0 | 2022-02-14 |  | Proof of Concept, runs locally
|  | 0.1.1-poc | Unreleased | 0 | 4 | 10 | 0 | 2022-03-01 |  | Added developer configuration files
|  | 0.2-android | Unreleased | 0 | 4 | 36 | 0 | 2022-03-28 |  | Barebones Android app added
|  | 0.2-ios | Unreleased | 3 | 1 | 27 | 0 | 2022-03-26 |  | Barebones iOS app added
|  | 0.3-alpha | Released | 10 | 3 | 20 | 0 | 2022-05-16 | 2022-09-01 | Alpha version
|  | 0.4-alpha | Released | 7 | 5 | 16 | 0 | 2022-09-07 | 2022-11-06
|  | 0.5-alpha | Released | 4 | 14 | 42 | 0 | 2022-11-10 | 2023-02-17
Calm Birds | BIRDS
Concertly | CONCERTLY | 0.1-local | Archived | 12 | 0 | 17 | 0 | 2021-03-14 | 2021-04-30 | Local website skeleton
|  | 0.2-local | Archived | 2 | 8 | 11 | 0 | 2021-05-02 | 2021-05-10 | Frontend updated
|  | 0.2.1-local | Archived | 0 | 1 | 6 | 0 | 2021-05-13 | 2021-05-22 | Fixed broken links
|  | 0.2.2-local | Archived | 4 | 1 | 5 | 0 | 2021-05-23 | 2021-06-01 | Fixed padding on buttons
|  | 0.3-local | Archived | 0 | 2 | 23 | 0 | 2021-06-18 | 2021-09-02 | Redesign
|  | 0.4-local | Archived | 9 | 8 | 18 | 0 | 2021-09-05 | 2021-10-08 | Optimizations
|  | 0.5-local | Archived | 0 | 0 | 0 | 0 | 2021-10-11
E-Bank Portal | EBANK | 1.0.0 | Released | 0 | 0 | 7 | 0 | 2023-05-04 | 2023-07-17 | Public release
|  | 1.1.0 | Released | 3 | 2 | 5 | 0 | 2023-10-21 | 2024-03-12 | Stability fixes
|  | 1.2.0 | Released | 1 | 0 | 2 | 0 | 2024-03-17 | 2024-04-01 | Minor fixes
|  | 1.3.0 | Released | 2 | 2 | 15 | 0 | 2024-05-29 | 2024-10-06 | UI update
|  | 1.4.0 | Unreleased | 15 | 9 | 20 | 0 | 2025-01-12
Created at 07/Jul/25 2:15 PM by Roland Traier-Kiss [Midori] with Better Excel Exporter for Jira Cloud
help »