## Projects
Sum of Story Points
| BFB | RACK | Grand Total
Done | 711 | 326 | 1037
Bug | 27 | 74 | 101
Story | 135 | 13 | 148
Sub-task | 227 | 196 | 423
Task | 322 | 43 | 365
In Progress | 175 | 77 | 252
Bug | 47 | 21 | 68
Story | 48 | 26 | 74
Sub-task | 9 | 19 | 28
Task | 71 | 11 | 82
To Do | 83 | 130 | 213
Bug |  | 69 | 69
Story | 13 |  | 13
Sub-task | 14 | 59 | 73
Task | 56 | 2 | 58
Grand Total | 969 | 533 | 1502

## Assignees
Sum of Story Points
| BFB | RACK | Grand Total
To Do | 83 | 130 | 213
Casey Ford | 26 | 68 | 94
Dalia Lens | 42 | 24 | 66
Levente Szabo | 3 | 23 | 26
Owen Klyed | 4 |  | 4
Robert Mongose | 8 | 15 | 23
In Progress | 175 | 77 | 252
Casey Ford | 22 | 5 | 27
Dalia Lens | 77 | 19 | 96
Levente Szabo | 32 |  | 32
Owen Klyed | 8 | 26 | 34
Robert Mongose | 36 | 27 | 63
Done | 711 | 326 | 1037
Casey Ford | 40 | 70 | 110
Dalia Lens | 331 | 71 | 402
Levente Szabo | 36 | 56 | 92
Owen Klyed | 88 | 47 | 135
Robert Mongose | 216 | 82 | 298
Grand Total | 969 | 533 | 1502

## Epics
Sum of Story Points
| Done | In Progress | To Do | Grand Total
Performace ready for 100K users | 400 | 69 | 161 | 630
Detect DDoS attacks before they happen | 303 | 80 | 52 | 435
Launching beem4biz.com | 255 | 66 |  | 321
"Products" landing page optimization | 79 | 37 |  | 116
Grand Total | 1037 | 252 | 213 | 1502

## Sprints
Sum of Story Points
BVP Validation Sprint | 335
Feedback form optimization | 252
Marketing and customer rel | 244
Security | 435
Webdesign upgrade | 236
Grand Total | 1502

## Issues
Key | Project Key | Issue Type | Priority | Status | Assignee | Component/s | Version/s | Epic (Link) | Sprint | Business Value | Story Points | Flagged
BFB-1 | BFB | Task | Low | Done | Dalia Lens | Landing Page, website design | 1 | "Products" landing page optimization | Webdesign upgrade | customfield_10203 not found | 13
BFB-10 | BFB | Task | Medium | In Progress | Dalia Lens | Landing Page, website design | 1 | "Products" landing page optimization | BVP Validation Sprint | customfield_10203 not found | 2
BFB-107 | BFB | Task | Low | In Progress | Casey Ford | Landing Page, website design | 1 | "Products" landing page optimization | Marketing and customer rel | customfield_10203 not found | 1
BFB-109 | BFB | Task | Medium | In Progress | Levente Szabo | Landing Page, website design | 1 | "Products" landing page optimization | Marketing and customer rel | customfield_10203 not found | 1
BFB-11 | BFB | Task | Medium | Done | Dalia Lens | Landing Page, website design | 1 | "Products" landing page optimization | Marketing and customer rel | customfield_10203 not found | 13
BFB-110 | BFB | Task | Low | In Progress | Casey Ford | Landing Page, website design | 1 | "Products" landing page optimization | Marketing and customer rel | customfield_10203 not found | 5
BFB-114 | BFB | Task | Low | In Progress | Dalia Lens | Landing Page, website design | 1 | "Products" landing page optimization | Webdesign upgrade | customfield_10203 not found | 5
BFB-115 | BFB | Task | Low | In Progress | Dalia Lens | Landing Page, website design | 1 | "Products" landing page optimization | Webdesign upgrade | customfield_10203 not found | 13
BFB-118 | BFB | Bug | Medium | In Progress | Dalia Lens | Landing Page, website design | 1 | Launching beem4biz.com | Feedback form optimization | customfield_10203 not found | 5
BFB-12 | BFB | Task | Low | Done | Dalia Lens | Landing Page, website design | 1 | Launching beem4biz.com | BVP Validation Sprint | customfield_10203 not found | 8
BFB-13 | BFB | Task | Medium | Done | Dalia Lens | Landing Page, website design | 1 | Launching beem4biz.com | Feedback form optimization | customfield_10203 not found | 6
BFB-14 | BFB | Task | Medium | In Progress | Levente Szabo | Landing Page, website design | 1 | Launching beem4biz.com | BVP Validation Sprint | customfield_10203 not found | 6
BFB-15 | BFB | Task | Lowest | Done | Robert Mongose | Landing Page, website design | 1 | Launching beem4biz.com | Webdesign upgrade | customfield_10203 not found | 34
BFB-16 | BFB | Task | Medium | Done | Robert Mongose | Landing Page, website design | 1 | Launching beem4biz.com | Webdesign upgrade | customfield_10203 not found | 21
BFB-17 | BFB | Task | Low | Done | Robert Mongose | Landing Page, website design | 1 | Launching beem4biz.com | Webdesign upgrade | customfield_10203 not found | 89
BFB-18 | BFB | Task | Medium | Done | Dalia Lens | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | BVP Validation Sprint | customfield_10203 not found | 13
BFB-19 | BFB | Task | Medium | In Progress | Levente Szabo | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | BVP Validation Sprint | customfield_10203 not found | 4
BFB-20 | BFB | Task | Medium | Done | Robert Mongose | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | BVP Validation Sprint | customfield_10203 not found | 4
BFB-21 | BFB | Story | Highest | Done | Levente Szabo | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | Webdesign upgrade | customfield_10203 not found | 1
BFB-22 | BFB | Task | Medium | In Progress | Robert Mongose | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | Webdesign upgrade | customfield_10203 not found | 13
BFB-23 | BFB | Story | Medium | In Progress | Robert Mongose | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | Webdesign upgrade | customfield_10203 not found | 21
BFB-24 | BFB | Story | High | Done | Dalia Lens | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | Webdesign upgrade | customfield_10203 not found | 21
BFB-26 | BFB | Story | Medium | In Progress | Casey Ford | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | Marketing and customer rel | customfield_10203 not found | 3
BFB-27 | BFB | Story | Low | In Progress | Casey Ford | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | Marketing and customer rel | customfield_10203 not found | 5
BFB-3 | BFB | Story | High | Done | Owen Klyed | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | Feedback form optimization | customfield_10203 not found | 1
BFB-30 | BFB | Task | Low | In Progress | Casey Ford | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | Marketing and customer rel | customfield_10203 not found | 3
BFB-35 | BFB | Story | Medium | Done | Owen Klyed | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | BVP Validation Sprint | customfield_10203 not found | 13
BFB-36 | BFB | Story | Medium | Done | Owen Klyed | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | BVP Validation Sprint | customfield_10203 not found | 13
BFB-37 | BFB | Story | Medium | Done | Owen Klyed | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | BVP Validation Sprint | customfield_10203 not found | 3
BFB-38 | BFB | Story | Low | Done | Dalia Lens | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | BVP Validation Sprint | customfield_10203 not found | 5
BFB-4 | BFB | Story | Highest | Done | Owen Klyed | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | BVP Validation Sprint | customfield_10203 not found | 2
BFB-5 | BFB | Story | Lowest | Done | Owen Klyed | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | BVP Validation Sprint | customfield_10203 not found | 21
BFB-8 | BFB | Story | Medium | In Progress | Dalia Lens | Android App, iOS App, Landing Page | 1 | Launching beem4biz.com | BVP Validation Sprint | customfield_10203 not found | 6
BFB-9 | BFB | Story | Medium | Done | Dalia Lens | Backend | 1.1 | Performace ready for 100K users | Webdesign upgrade | customfield_10203 not found | 5
BFB-96 | BFB | Story | Medium | Done | Dalia Lens | Backend | 1.1 | Performace ready for 100K users | Marketing and customer rel | customfield_10203 not found | 21
BFB-97 | BFB | Story | Medium | Done | Dalia Lens | Backend | 1.1 | Performace ready for 100K users | Marketing and customer rel | customfield_10203 not found | 3
BFB-99 | BFB | Story | Medium | Done | Casey Ford | Backend | 1.1 | Performace ready for 100K users | Marketing and customer rel | customfield_10203 not found | 5
BFB-100 | BFB | Task | Medium | Done | Levente Szabo | Backend | 1.1 | Performace ready for 100K users | Marketing and customer rel |  | 21
BFB-101 | BFB | Bug | Medium | In Progress | Dalia Lens | Backend | 1.1 | Performace ready for 100K users | Marketing and customer rel |  | 1
BFB-102 | BFB | Task | Medium | In Progress | Casey Ford | Backend | 1.1 | Performace ready for 100K users | Marketing and customer rel |  | 5
BFB-103 | BFB | Task | Low | In Progress | Dalia Lens | Backend | 1.1 | Performace ready for 100K users | Marketing and customer rel |  | 13
BFB-104 | BFB | Bug | Low | Done | Dalia Lens | Backend | 1.1 | Performace ready for 100K users | Marketing and customer rel |  | 5
BFB-105 | BFB | Bug | Low | In Progress | Dalia Lens | Backend | 1.1 | Performace ready for 100K users | Marketing and customer rel |  | 5
BFB-106 | BFB | Bug | Low | In Progress | Dalia Lens | Backend | 1.1 | Performace ready for 100K users | Marketing and customer rel |  | 13
BFB-107 | RACK | Bug | Medium | To Do | Dalia Lens | Backend | 1.1 | Performace ready for 100K users | Marketing and customer rel |  | 21
BFB-108 | BFB | Bug | Medium | In Progress | Levente Szabo | Backend | 1.2 | Performace ready for 100K users | Marketing and customer rel |  | 21
BFB-109 | RACK | Bug | Medium | Done | Robert Mongose | Backend | 1.2 | Performace ready for 100K users | Marketing and customer rel |  | 1
BFB-110 | RACK | Bug | Medium | Done | Robert Mongose | Backend | 1.2 | Performace ready for 100K users | Marketing and customer rel |  | 21
BFB-111 | BFB | Task | Medium | To Do | Robert Mongose | Backend | 1.2 | Performace ready for 100K users | Marketing and customer rel |  | 5
BFB-112 | BFB | Task | Medium | Done | Dalia Lens | Backend | 1.2 | Performace ready for 100K users | Marketing and customer rel |  | 2
BFB-113 | BFB | Task | High | Done | Levente Szabo | Backend | 1.2 | Performace ready for 100K users | Marketing and customer rel |  | 2
BFB-114 | BFB | Task | High | Done | Robert Mongose | Backend | 1.2 | Performace ready for 100K users | Marketing and customer rel |  | 13
BFB-115 | RACK | Bug | Medium | Done | Levente Szabo | Backend | 1.2 | Performace ready for 100K users | Marketing and customer rel |  | 34
BFB-116 | RACK | Bug | Medium | To Do | Robert Mongose | Backend | 1.2 | Performace ready for 100K users | Marketing and customer rel |  | 1
BFB-117 | RACK | Bug | Medium | Done | Robert Mongose | Backend | 1.2 | Performace ready for 100K users | BVP Validation Sprint |  | 2
BFB-118 | BFB | Story | Low | Done | Dalia Lens | Backend | 1.2 | Performace ready for 100K users | BVP Validation Sprint |  | 8
BFB-119 | RACK | Bug | Highest | To Do | Casey Ford | Backend | 1.2 | Performace ready for 100K users | BVP Validation Sprint |  | 13
BFB-120 | RACK | Bug | Lowest | To Do | Casey Ford | Backend | 1.2 | Performace ready for 100K users | BVP Validation Sprint |  | 34
BFB-121 | RACK | Bug | Medium | Done | Owen Klyed | Backend | 1.2 | Performace ready for 100K users | BVP Validation Sprint |  | 13
BFB-122 | BFB | Story | Medium | To Do | Casey Ford | Backend | 1.2 | Performace ready for 100K users | BVP Validation Sprint |  | 13
BFB-123 | BFB | Story | Medium | In Progress | Owen Klyed | Backend | 1.2 | Performace ready for 100K users | BVP Validation Sprint |  | 3
BFB-124 | RACK | Bug | Medium | Done | Owen Klyed | Backend | 1.2 | Performace ready for 100K users | BVP Validation Sprint |  | 3
BFB-125 | BFB | Task | Medium | To Do | Owen Klyed | Backend | 1.2 | Performace ready for 100K users | BVP Validation Sprint |  | 1
BFB-126 | BFB | Bug | Medium | Done | Dalia Lens | Backend | 2 | Performace ready for 100K users | BVP Validation Sprint |  | 13
BFB-127 | BFB | Bug | Medium | Done | Owen Klyed | Backend | 2 | Performace ready for 100K users | BVP Validation Sprint |  | 5
BFB-128 | BFB | Bug | Low | Done | Owen Klyed | Backend | 2 | Performace ready for 100K users | BVP Validation Sprint |  | 2
BFB-129 | BFB | Bug | Low | Done | Dalia Lens | Backend | 2 | Performace ready for 100K users | BVP Validation Sprint |  | 2
BFB-130 | BFB | Sub-task | Low | Done | Dalia Lens | Backend | 2 | Performace ready for 100K users | BVP Validation Sprint |  | 3
BFB-131 | BFB | Sub-task | Low | Done | Dalia Lens | Backend | 2 | Performace ready for 100K users | BVP Validation Sprint |  | 34
BFB-132 | BFB | Sub-task | Medium | In Progress | Dalia Lens | Backend | 2 | Performace ready for 100K users | BVP Validation Sprint |  | 5
BFB-133 | BFB | Sub-task | Medium | Done | Casey Ford | Backend | 2 | Performace ready for 100K users | BVP Validation Sprint |  | 13
BFB-134 | BFB | Sub-task | Medium | Done | Levente Szabo | Backend | 2 | Performace ready for 100K users | BVP Validation Sprint |  | 5
BFB-135 | BFB | Sub-task | Medium | Done | Dalia Lens | Backend | 2 | Performace ready for 100K users | Feedback form optimization |  | 55
BFB-136 | RACK | Sub-task | Medium | Done | Casey Ford | Backend | 2 | Performace ready for 100K users | Feedback form optimization |  | 6
BFB-137 | BFB | Task | Medium | Done | Dalia Lens | Backend | 2 | Performace ready for 100K users | Feedback form optimization |  | 21
BFB-138 | RACK | Sub-task | High | In Progress | Dalia Lens | Backend | 2 | Performace ready for 100K users | Feedback form optimization |  | 1
BFB-139 | BFB | Task | High | To Do | Dalia Lens | Backend | 2 | Performace ready for 100K users | Feedback form optimization |  | 21
BFB-140 | BFB | Task | Medium | To Do | Dalia Lens | Backend | 2 | Performace ready for 100K users | Feedback form optimization |  | 21
BFB-141 | RACK | Sub-task | Medium | Done | Dalia Lens | Backend | 2 | Performace ready for 100K users | Feedback form optimization |  | 2
BFB-142 | RACK | Sub-task | Medium | To Do | Levente Szabo | Frontend | 2 | Performace ready for 100K users | Feedback form optimization |  | 21
BFB-143 | RACK | Sub-task | Low | To Do | Robert Mongose | Frontend | 2 | Performace ready for 100K users | Feedback form optimization |  | 5
BFB-144 | RACK | Sub-task | Highest | To Do | Robert Mongose | Frontend | 2 | Performace ready for 100K users | Feedback form optimization |  | 2
BFB-145 | BFB | Bug | Lowest | In Progress | Robert Mongose | Frontend | 2 | Performace ready for 100K users | Feedback form optimization |  | 2
BFB-146 | RACK | Sub-task | Medium | Done | Dalia Lens | Frontend | 2.1 | Performace ready for 100K users | Feedback form optimization |  | 21
BFB-147 | RACK | Sub-task | Medium | Done | Levente Szabo | Frontend | 2.1 | Performace ready for 100K users | Feedback form optimization |  | 2
BFB-148 | BFB | Task | Medium | To Do | Robert Mongose | Frontend | 2.1 | Performace ready for 100K users | Feedback form optimization |  | 3
BFB-149 | BFB | Task | Medium | Done | Levente Szabo | Frontend | 2.1 | Performace ready for 100K users | Feedback form optimization |  | 2
BFB-150 | BFB | Task | Medium | Done | Robert Mongose | Frontend | 2.1 | Performace ready for 100K users | Feedback form optimization |  | 34
BFB-151 | BFB | Task | Medium | Done | Robert Mongose | Frontend | 2.1 | Performace ready for 100K users | Feedback form optimization |  | 21
BFB-152 | RACK | Sub-task | Medium | Done | Dalia Lens | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 2
BFB-153 | RACK | Sub-task | Medium | To Do | Casey Ford | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 21
BFB-154 | RACK | Sub-task | Low | Done | Casey Ford | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 21
BFB-155 | BFB | Story | Low | Done | Owen Klyed | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 13
BFB-156 | BFB | Sub-task | Low | To Do | Casey Ford | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 13
BFB-157 | BFB | Sub-task | Low | To Do | Owen Klyed | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 1
BFB-158 | BFB | Sub-task | Medium | Done | Owen Klyed | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 13
BFB-159 | BFB | Story | Medium | In Progress | Owen Klyed | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 5
BFB-160 | BFB | Story | Medium | In Progress | Dalia Lens | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 5
BFB-161 | BFB | Sub-task | Medium | Done | Owen Klyed | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 2
BFB-162 | BFB | Task | Medium | To Do | Owen Klyed | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 2
BFB-163 | BFB | Sub-task | Medium | Done | Dalia Lens | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 5
BFB-164 | BFB | Sub-task | High | Done | Dalia Lens | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 21
BFB-165 | BFB | Sub-task | High | Done | Dalia Lens | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 1
BFB-166 | BFB | Sub-task | Medium | Done | Dalia Lens | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 21
BFB-167 | BFB | Sub-task | Medium | Done | Casey Ford | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 1
BFB-168 | BFB | Sub-task | Medium | Done | Levente Szabo | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 5
BFB-169 | BFB | Sub-task | Low | In Progress | Dalia Lens | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 1
BFB-170 | BFB | Sub-task | Highest | Done | Casey Ford | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 21
BFB-171 | BFB | Sub-task | Lowest | Done | Dalia Lens | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 13
BFB-172 | BFB | Sub-task | Medium | Done | Dalia Lens | Frontend | 2.1 | Detect DDoS attacks before they happen | Security |  | 13
BFB-173 | BFB | Sub-task | Medium | Done | Dalia Lens | Frontend | 3 | Detect DDoS attacks before they happen | Security |  | 1
BFB-174 | BFB | Task | Medium | Done | Dalia Lens | Frontend | 3 | Detect DDoS attacks before they happen | Security |  | 5
BFB-175 | BFB | Sub-task | Medium | In Progress | Dalia Lens | Frontend | 3 | Detect DDoS attacks before they happen | Security |  | 3
BFB-176 | BFB | Task | Medium | To Do | Levente Szabo | Frontend | 3 | Detect DDoS attacks before they happen | Security |  | 3
BFB-177 | RACK | Task | Highest | To Do | Robert Mongose | Frontend | 3 | Detect DDoS attacks before they happen | Security |  | 2
BFB-178 | RACK | Sub-task | Lowest | Done | Robert Mongose | Frontend | 3 | Detect DDoS attacks before they happen | Security |  | 34
BFB-179 | RACK | Sub-task | Medium | To Do | Robert Mongose | Frontend | 3 | Detect DDoS attacks before they happen | Security |  | 5
BFB-180 | RACK | Sub-task | Medium | To Do | Dalia Lens | Frontend | 3 | Detect DDoS attacks before they happen | Security |  | 3
BFB-181 | RACK | Sub-task | Medium | To Do | Levente Szabo | Frontend | 3 | Detect DDoS attacks before they happen | Security |  | 2
BFB-182 | RACK | Bug | Medium | In Progress | Robert Mongose | Frontend | 3 | Detect DDoS attacks before they happen | Security |  | 21
BFB-183 | RACK | Sub-task | Medium | Done | Levente Szabo | Frontend | 3 | Detect DDoS attacks before they happen | Security |  | 1
BFB-184 | RACK | Sub-task | Medium | Done | Robert Mongose | Frontend | 3 | Detect DDoS attacks before they happen | Security |  | 21
BFB-185 | RACK | Task | Medium | In Progress | Robert Mongose | Frontend | 3 | Detect DDoS attacks before they happen | Security |  | 1
BFB-186 | RACK | Task | Medium | Done | Dalia Lens | Frontend | 1 | Detect DDoS attacks before they happen | Security |  | 5
BFB-187 | RACK | Task | Low | Done | Casey Ford | Frontend | 1 | Detect DDoS attacks before they happen | Security |  | 1
BFB-188 | RACK | Task | Low | Done | Casey Ford | Frontend | 1 | Detect DDoS attacks before they happen | Security |  | 34
BFB-189 | RACK | Sub-task | Low | Done | Owen Klyed | Frontend | 1 | Detect DDoS attacks before they happen | Security |  | 13
BFB-190 | RACK | Sub-task | Low | In Progress | Casey Ford | Frontend | 1 | Detect DDoS attacks before they happen | Security |  | 5
BFB-191 | RACK | Sub-task | Medium | Done | Owen Klyed | Frontend | 1.1 | Detect DDoS attacks before they happen | Security |  | 2
BFB-192 | RACK | Story | Medium | Done | Owen Klyed | Frontend | 1.1 | Detect DDoS attacks before they happen | Security |  | 13
BFB-193 | RACK | Sub-task | Medium | In Progress | Owen Klyed | Frontend | 1.1 | Detect DDoS attacks before they happen | Security |  | 5
BFB-194 | RACK | Sub-task | Medium | In Progress | Dalia Lens | Frontend | 1.1 | Detect DDoS attacks before they happen | Security |  | 3
BFB-195 | RACK | Sub-task | Medium | Done | Owen Klyed | Frontend | 1.1 | Detect DDoS attacks before they happen | Security |  | 3
BFB-196 | RACK | Story | Medium | In Progress | Owen Klyed | Frontend | 1.1 | Detect DDoS attacks before they happen | Security |  | 21
BFB-197 | RACK | Story | High | In Progress | Dalia Lens | Frontend | 1.1 | Detect DDoS attacks before they happen | Security |  | 5
BFB-198 | RACK | Sub-task | High | Done | Dalia Lens | Frontend | 1.1 | Detect DDoS attacks before they happen | Security |  | 3
BFB-199 | RACK | Task | Medium | In Progress | Dalia Lens | Frontend | 1.1 | Detect DDoS attacks before they happen | Security |  | 5
BFB-200 | RACK | Sub-task | Medium | Done | Dalia Lens | Frontend | 1.1 | Detect DDoS attacks before they happen | Security |  | 13
BFB-201 | RACK | Sub-task | Medium | Done | Casey Ford | Frontend | 1.1 | Detect DDoS attacks before they happen | Security |  | 2
BFB-202 | RACK | Sub-task | Low | Done | Levente Szabo | Frontend | 1.1 | "Products" landing page optimization | BVP Validation Sprint |  | 1
BFB-203 | RACK | Sub-task | Highest | Done | Dalia Lens | Frontend | 1.2 | "Products" landing page optimization | BVP Validation Sprint |  | 5
BFB-204 | RACK | Sub-task | Lowest | Done | Casey Ford | Frontend | 1.2 | "Products" landing page optimization | BVP Validation Sprint |  | 6
BFB-205 | RACK | Sub-task | Medium | Done | Dalia Lens | Frontend | 1.2 | "Products" landing page optimization | BVP Validation Sprint |  | 2
BFB-206 | RACK | Sub-task | Medium | In Progress | Dalia Lens | Frontend | 1.2 | "Products" landing page optimization | BVP Validation Sprint |  | 5
BFB-207 | RACK | Sub-task | Medium | Done | Dalia Lens | Frontend | 1.2 | "Products" landing page optimization | BVP Validation Sprint |  | 8
BFB-208 | RACK | Sub-task | Medium | Done | Dalia Lens | Frontend | 1.2 | "Products" landing page optimization | BVP Validation Sprint |  | 5
BFB-209 | RACK | Sub-task | Medium | Done | Dalia Lens | Frontend | 1.2 | "Products" landing page optimization | BVP Validation Sprint |  | 2
BFB-210 | RACK | Sub-task | Low | Done | Levente Szabo | Frontend | 1.2 | "Products" landing page optimization | BVP Validation Sprint |  | 13
BFB-211 | RACK | Task | Highest | In Progress | Robert Mongose | Frontend | 1.2 | "Products" landing page optimization | BVP Validation Sprint |  | 2
BFB-212 | RACK | Sub-task | Lowest | Done | Robert Mongose | Frontend | 1.2 | "Products" landing page optimization | BVP Validation Sprint |  | 3
BFB-213 | RACK | Task | Medium | In Progress | Robert Mongose | Frontend | 1.2 | "Products" landing page optimization | BVP Validation Sprint |  | 3
BFB-214 | RACK | Task | Medium | Done | Dalia Lens | Frontend | 1.2 | "Products" landing page optimization | BVP Validation Sprint |  | 3
BFB-215 | RACK | Sub-task | Low | Done | Levente Szabo | Frontend | 1.2 | "Products" landing page optimization | BVP Validation Sprint |  | 5