## Issue Navigator
Key | T | Summary | Assignee | Due | Status | Cost of Delay ($) | Story Points | Created | Labels
| Memo | 1 GROUP BY SPRINT, GROUP BY ASSIGNEE, SORT BY STORY POINTS
| Folder | 2 ChargePool Android app 3.4.0
2.1 Casey Ford
PF-63 | Story | 2.1.1 As a mobile app user, I want to be able to plan a route | Casey Ford | 2020-06-15 | Under development | 86500 | 23 | 2020-03-30 14:02
PF-60 | Task | 2.1.2 Automatically map locations, devices and connectors | Casey Ford | 2020-06-11 | Under development | 35000 | 19 | 2020-03-30 13:54 | geo, mapping
2.2 Robert Mongose
PF-62 | Task | 2.2.1 Allow filtering chargers by capacity | Robert Mongose | 2020-06-16 | Under development | 2545 | 12 | 2020-03-30 14:02 | app-features, chargers, ui
2.3 Zoe Barnes
PF-59 | Task | 2.3.1 Enable EV drivers to locate and navigate to charging points | Zoe Barnes | 2020-03-26 | To Do | 12870 | 49 | 2020-03-30 13:52 | app-features, ui, user-experience
PF-61 | Task | 2.3.2 Show charge points from ChargePool network and smaller providers | Zoe Barnes | 2020-06-16 | Under development | 3456 | 21 | 2020-03-30 14:01
| Folder | 2.4 Unassigned
PF-64 | Task | 2.4.1 Implement list view of chargers |  | 2020-05-26 | To Do | 1245 | 4 | 2020-03-30 14:03 | chargers, coverage
| Folder | 3 City Chargers
3.1 Bob Mitchell
PF-41 | Task | 3.1.1 Express Plus platform shares power intelligently among two stations | Bob Mitchell | 2020-05-13 | To Do | 19400 | 42 | 2015-05-16 03:03 | chargers, infrastructure
PF-40 | Task | 3.1.2 Start a connected Network Operation Center (NOC) | Bob Mitchell | 2020-04-29 | Under development | 250000 | 34 | 2015-11-24 18:25 | coverage
PF-52 | Task | 3.1.3 98% annual uptime guarantee | Bob Mitchell | 2020-05-05 | Under development | 34910 | 12 | 2015-05-03 14:16 | experience
3.2 Casey Ford
PF-38 | Task | 3.2.1 Access to drivers and network | Casey Ford | 2020-05-11 | Under development | 23870 | 24 | 2015-09-30 23:33 | coverage
PF-46 | Task | 3.2.2 24X7 proactive station health monitoring | Casey Ford | 2020-05-08 | Under development | 123560 | 5 | 2015-05-17 16:39 | chargers, infrastructure
3.3 Robert Mongose
PF-44 | Task | 3.3.1 Detailed quarterly reports of stations performance metrics | Robert Mongose | 2020-04-29 | Under development | 34910 | 24 | 2015-08-24 09:14 | reporting, user-data
PF-45 | Task | 3.3.2 Monthly reports of station’s performance metrics | Robert Mongose | 2020-05-11 | To Do | 4500 | 18 | 2015-08-22 19:38 | reporting, user-data
| Folder | 4 Faster home charging
| Folder | 4.1 Unassigned
| Memo | 4.1.1 Assign these jobs ASAP!
PF-67 | Task | 4.1.2 Access restriction and permissions for charger console |  | 2020-06-08 | To Do | 45600 | 26 | 2020-03-30 14:33 | chargers
PF-65 | Task | 4.1.3 Compatibility with Type 2 tethered socket |  | 2020-05-27 | To Do | 234500 | 22 | 2020-03-30 14:11 | chargers, infrastructure, integration
PF-66 | Task | 4.1.4 Allow swapping from Type 1 to Type 2 connector |  | 2020-06-09 | To Do | 10000 | 12 | 2020-03-30 14:29 | infrastructure, interactions
| Folder | 5 Roadside Infrastructure
5.1 Bob Mitchell
PF-34 | Task | 5.1.1 Connect up the power distribution blocks to power service provider | Bob Mitchell | 2020-04-29 | To Do | 25000 | 78 | 2015-09-24 17:10
PF-29 | Task | 5.1.2 Test capacity to deliver full output power continuously | Bob Mitchell | 2020-05-05 | Under development | 3000 | 16 | 2016-02-12 15:51 | infrastructure
PF-42 | Task | 5.1.3 Single vehicle charge up to 500 kilowatts | Bob Mitchell | 2020-04-29 | Under development | 19883 | 14 | 2016-04-05 23:08 | chargers
5.2 Casey Ford
PF-49 | Task | 5.2.1 Support charging in towns and remote areas | Casey Ford | 2020-04-29 | To Do | 450900 | 28 | 2015-07-24 01:18 | chargers, infrastructure, integration
PF-43 | Task | 5.2.2 Detailed reporting feature for premium customers | Casey Ford | 2020-04-29 | To Do | 19883 | 28 | 2015-08-27 12:25 | reporting
5.3 Robert Mongose
PF-30 | Task | 5.3.1 Setup bi-directional energy meters | Robert Mongose | 2020-04-29 | Under installation | 6000 | 32 | 2016-02-07 23:04
5.4 Zoe Barnes
PF-37 | Task | 5.4.1 Roaming and interoperability | Zoe Barnes | 2020-05-05 | Under development | 25000 | 42 | 2015-09-29 09:57 | infrastructure, integration
| Folder | 6 No value
| Folder | 6.1 Not an issue
43 | [5 empty] | 1472532 | 585
Created at 09/Apr/20 2:29 PM by Levente Szabo with Better Excel Exporter for Jira
help »