## Issue Navigator
Key | Summary | P | Test Case | Name | Priority | Status | Objective | Precondition | Execution | Status | Assigned To | Executed By | Executed On | Comment
CWT-1 | Test the behavior of required fields | Medium | CWT-T1 | Required Fields Test | High | Approved | Test the behavior of required fields | Form is implemented and deployed (CWT-17). | CWT-E21 | Pass | David Parker | David Parker | 2025-05-02
[9 empty] | CWT-E1 | Pass | Matthew Bates | Matthew Bates | 2025-05-04
CWT-2 | Enter different data types | Medium | CWT-T2 | Data Types Test | High | Approved | Enter different data types | Form is implemented and deployed (CWT-17). | CWT-E35 | Fail | John Hopkins | Quentin Ortiz | 2025-05-06 | Only the data entry form is tested in this execution
[9 empty] | CWT-E2 | Not Executed
CWT-3 | Use various field widths | Medium | CWT-T3 | Field Widths Test | High | Approved | Use various field widths | Form is implemented and deployed (CWT-17). | CWT-E34 | Blocked | Quentin Ortiz | Quentin Ortiz | 2025-05-08
[9 empty] | CWT-E3 | Fail | Matthew Bates | Matthew Bates | 2025-05-09 | This should pass, as some names are only 2-3 characters long
CWT-4 | Onscreen instructions | Medium | CWT-T4 | Onscreen Instructions Test | Low | Draft | Onscreen instructions | CWT-18 has been deployed. | CWT-E20 | Blocked | David Parker | David Parker | 2025-05-10
[9 empty] | CWT-E4 | Pass | John Hopkins | Matthew Bates | 2025-05-12
CWT-5 | Keep onscreen instructions brief | Medium | CWT-T5 | Onscreen Instructions Clarity Test | Low | Deprecated | Keep onscreen instructions brief | CWT-18 has been deployed. | CWT-E33 | Not Executed
[9 empty] | CWT-E19 | Fail | David Parker | David Parker | 2025-05-13
[9 empty] | CWT-E5 | Blocked | John Hopkins | Matthew Bates | 2025-05-13
CWT-6 | Progress bars appearance at different scenarios | Medium | CWT-T6 | Image Upload Test | Normal | Draft | Progress bars' appearance at different scenarios | Form is implemented and deployed (CWT-17). | CWT-E6 | Blocked | Matthew Bates | Matthew Bates | 2025-05-13
CWT-7 | Same document opened multiple times | Medium | CWT-T7 | Image Download Test | Normal | Approved | Verify the persistence of attachments | Form is implemented and deployed (CWT-17). | CWT-E7 | Fail | Matthew Bates | Matthew Bates | 2025-05-14 | Created a bug to look into the cause of the failed step
CWT-8 | Cosmetic inconsistencies | Medium | CWT-T8 | Find Cosmetic Inconsistencies | Low | Draft | Cosmetic inconsistencies | - | CWT-E32 | Pass | Quentin Ortiz | Quentin Ortiz | 2025-05-16
[9 empty] | CWT-E18 | Fail | David Parker | David Parker | 2025-05-16 | Logos should be consistent (one color) on all pages
[9 empty] | CWT-E8 | Pass | Matthew Bates | Matthew Bates | 2025-05-16
CWT-9 | Abbreviation inconsistencies | Medium | CWT-T9 | Find Abbreviation Inconsistencies | Low | Draft | Abbreviation inconsistencies | - | CWT-E9 | Pass | John Hopkins | Matthew Bates | 2025-05-17
CWT-10 | Confirmations on saving forms | Medium | CWT-T10 | Confirmations Test | High | Approved | Confirmations on saving forms | Form is implemented and deployed (CWT-17). | CWT-E10 | Blocked | Matthew Bates | Matthew Bates | 2025-05-19 | Error message is misleading, should be rephrased
CWT-11 | Use type ahead feature for form filling | Medium | CWT-T11 | Typeahead Test | Normal | Draft | Use type ahead feature for form filling | Form is implemented and deployed (CWT-17). | CWT-E31 | Not Executed
[9 empty] | CWT-E11 | Not Executed
CWT-12 | Try table scrolling edge cases | Medium | CWT-T12 | Scrolling Edge Cases Test | Normal | Deprecated | Try table scrolling edge cases | - | CWT-E30 | Pass | Quentin Ortiz | Quentin Ortiz | 2025-06-02
[9 empty] | CWT-E12 | Fail | John Hopkins | Matthew Bates | 2025-06-12 | Table doesn’t work with the content on this page
CWT-13 | Error logging | Medium | CWT-T13 | Error Logging Test | High | Approved | Error logging | Form is implemented and deployed (CWT-17). | CWT-E17 | Pass | David Parker | David Parker | 2025-06-16
[9 empty] | CWT-E13 | Pass | Matthew Bates | Matthew Bates | 2025-06-19
CWT-14 | Try all shortcut keys | Medium | CWT-T14 | Shortcut Keys Test | Low | Draft | Try all shortcut keys | - | CWT-E16 | Pass | David Parker | David Parker | 2025-06-20
[9 empty] | CWT-E14 | Not Executed
CWT-15 | Invalid menu items | Medium | CWT-T15 | Invalid Menu Items Test | Low | Approved | Invalid menu items | - | CWT-E29 | Pass | Quentin Ortiz | Quentin Ortiz | 2025-07-02
[9 empty] | CWT-E15 | Not Executed
CWT-16 | Keyboard switching for number type fields on mobile | Medium | CWT-T16 | Mobile Number Keys Test | Low | Deprecated | Keyboard switching for number type fields on mobile | Form is implemented and deployed (CWT-17). | CWT-E36 | Pass | Matthew Bates | John Hopkins | 2025-07-16
CWT-23 | Load website with various connections quality | Medium | CWT-T23 | Mobile Accessibility Test | Low | Draft | Load website with various connections quality | - | CWT-E37 | Not Executed | Mitch Davis
CWT-24 | Try different browsers for compatibility | Medium | CWT-T24 | Browsers Compatibility Test | High | Deprecated | Try different browsers for compatibility | - | CWT-E38 | Pass | John Hopkins | John Hopkins | 2025-07-26
CWT-25 | Operating System compatibility | Medium | CWT-T25
CWT-26 | Response times at different connection speeds | Medium | CWT-T26 | Website Connectivity Test | Low | Draft | Response times at different connection speeds | - | CWT-E39 | Pass | Ryan Lee | John Hopkins | 2025-08-26
CWT-27 | Verify required SSL security compliance | Medium | CWT-T27 | SSL Verification | High | Approved | Verify required SSL security compliance | SSL certification has been added (CWT-20) | CWT-E40 | Fail |  | John Hopkins | 2025-09-06 | HIPAA recommended penetration testing has been delayed
CWT-28 | Database consistency | Medium | CWT-T28 | Database Consistency Test | High | Approved | Database consistency | - | CWT-E42 | Not Executed
CWT-29 | HTTP protocol used to maintain website cookies | Medium | CWT-T29 | HTTP Protocol Test | Normal | Deprecated | HTTP protocol used to maintain website cookies | - | CWT-E41 | Pass | David Parker | John Hopkins | 2025-09-26
CWT-30 | HTML consistency check | Medium | CWT-T30 | HTML Consistency Test | Low | Draft | HTML consistency check | - | CWT-E54 | Not Executed
24
Created at 26/Jun/25 2:10 PM by John Hopkins with Better Excel Exporter for Jira Cloud
help »