## Execution per Version
Execution | Execution Status
Test Cycle | UNEXECUTED | BLOCKED | WIP | FAIL | PASS | Grand Total
CWT | 5 | 2 | 4 | 9 | 15 | 35
Ad hoc | 4 | 1 | 2 | 4 | 8 | 19
Unscheduled | 1 |  |  | 3 | 4 | 8
v0.1 | 1 | 1 | 2 |  | 1 | 5
v0.3 | 1 |  |  |  |  | 1
v1.0 | 1 |  |  | 1 | 3 | 5
Regression | 1 |  | 1 | 2 | 3 | 7
v0.1 | 1 |  | 1 | 2 | 3 | 7
Sanity |  | 1 | 1 | 3 | 4 | 9
v0.1 |  | 1 | 1 | 2 | 4 | 8
v1.0 |  |  |  | 1 |  | 1
NVT | 5 | 3 | 4 | 11 | 16 | 39
GUI | 3 | 3 | 1 | 7 | 9 | 23
Unscheduled |  | 1 | 1 |  | 1 | 3
v0.1 | 1 | 1 |  | 2 | 2 | 6
v0.2 | 2 |  |  | 2 | 4 | 8
v0.3 |  |  |  | 3 | 2 | 5
v1.0 |  | 1 |  |  |  | 1
Usability | 2 |  | 3 | 4 | 7 | 16
Unscheduled | 1 |  | 1 | 2 | 4 | 8
v0.1 |  |  |  | 1 |  | 1
v0.2 |  |  |  | 1 | 3 | 4
v0.3 | 1 |  | 2 |  |  | 3
Grand Total | 10 | 5 | 8 | 20 | 31 | 74

## Execution History
Count of Execution ID | Execution Status
Executed On | BLOCKED | WIP | UNEXECUTED | FAIL | PASS | Grand Total
May
24 | 1 | 2 |  | 2 | 1 | 6
7 | 1 | 1 |  | 1 | 1 | 4
2 |  |  |  | 1 | 2 | 3
Jun
18 |  | 1 |  |  | 2 | 3
25 |  |  |  | 1 |  | 1
27 |  |  |  | 1 | 4 | 5
Jul
2 |  |  |  | 2 | 4 | 6
3 |  |  |  | 1 |  | 1
Aug
2 |  |  |  |  | 1 | 1
3 |  |  |  |  | 1 | 1
4 |  | 1 |  | 2 | 1 | 4
14 | 1 | 2 |  | 1 | 1 | 5
17 | 1 |  |  | 1 | 1 | 3
19 |  |  |  | 1 | 2 | 3
20 | 1 | 1 |  | 2 | 2 | 6
Sep
12 |  |  |  | 1 | 3 | 4
19 |  |  |  | 2 | 3 | 5
Oct
10 |  |  |  | 1 | 2 | 3
(Unexecuted)
(Unexecuted) |  |  | 10 |  |  | 10
Grand Total | 5 | 8 | 10 | 20 | 31 | 74

## Execution per Cycle
Execution | Execution Status
Test Cycle | UNEXECUTED | BLOCKED | WIP | FAIL | PASS | Grand Total
CWT | 5 | 2 | 4 | 9 | 15 | 35
Ad hoc | 4 | 1 | 2 | 4 | 8 | 19
Sanity |  | 1 | 1 | 3 | 4 | 9
Regression | 1 |  | 1 | 2 | 3 | 7
NVT | 5 | 3 | 4 | 11 | 16 | 39
GUI | 3 | 3 | 1 | 7 | 9 | 23
Usability | 2 |  | 3 | 4 | 7 | 16
Grand Total | 10 | 5 | 8 | 20 | 31 | 74

## Execution per Tester
Execution | Execution Status
Tester | UNEXECUTED | BLOCKED | WIP | FAIL | PASS | Grand Total
(Unexecuted) | 10 |  |  |  |  | 10
David Parker |  | 1 | 2 | 1 | 4 | 8
John Hopkins |  |  |  | 2 | 7 | 9
Katerina Gonzales |  | 1 | 2 | 5 | 7 | 15
Matthew Bates |  | 2 | 2 | 5 | 9 | 18
Quentin Ortiz |  | 1 | 2 | 7 | 4 | 14
Grand Total | 10 | 5 | 8 | 20 | 31 | 74

## Defect per Test
Values
Test | Sum of Execution Defects Count | Sum of Step Defects Count
CWT-1 / Test the behavior of required fields | 0 | 0
CWT-10 / Confirmations on saving forms | 0 | 0
CWT-11 / Use type ahead feature for form filling | 0 | 0
CWT-12 / Try table scrolling edge cases | 2 | 1
CWT-13 / Error logging | 0 | 0
CWT-14 / Try all shortcut keys | 0 | 0
CWT-15 / Invalid menu items | 0 | 0
CWT-16 / Keyboard switching for number type fields on mobile | 0 | 0
CWT-2 / Enter different data types | 1 | 2
CWT-23 / Load website with various connections quality | 0 | 0
CWT-24 / Try different browsers for compatibility | 0 | 0
CWT-26 / Response times at different connection speeds | 0 | 0
CWT-27 / Verify required SSL security compliance | 1 | 1
CWT-28 / Database consistency | 0 | 0
CWT-29 / HTTP protocol used to maintain website cookies | 0 | 0
CWT-3 / Use various field widths | 3 | 2
CWT-4 / Onscreen instructions | 1 | 1
CWT-5 / Keep onscreen instructions brief | 0 | 0
CWT-6 / Progress bars appearance at different scenarios | 1 | 1
CWT-7 / Same document opened multiple times | 1 | 1
CWT-8 / Cosmetic inconsistencies | 2 | 2
CWT-9 / Abbreviation inconsistencies | 0 | 0
NVT-1 / All fields on page should be aligned properly | 0 | 0
NVT-10 / Information filled by users should remain intact when there is error message on page submit | 2 | 2
NVT-11 / Check if proper field labels are used in error messages | 0 | 0
NVT-12 / Dropdown field values should be displayed in defined sort order | 0 | 0
NVT-13 / Tab and Shift+Tab order should work properly | 0 | 0
NVT-14 / Default radio options should be pre-selected on page load | 0 | 0
NVT-15 / Field specific help messages should be available | 2 | 2
NVT-16 / Check if correct fields are highlighted in case of errors | 0 | 0
NVT-17 / Check if dropdown list options are readable | 0 | 0
NVT-18 / All buttons on page should be accessible by keyboard shortcut | 0 | 0
NVT-19 / Check all pages for broken images | 0 | 0
NVT-2 / Numeric values should be right justified | 2 | 2
NVT-20 / Check all pages for broken links | 1 | 1
NVT-21 / All pages should have title | 0 | 0
NVT-22 / Confirmation messages should be displayed before performing any update or delete operation | 0 | 0
NVT-23 / Hour glass should be displayed when application is busy | 0 | 0
NVT-24 / Page text should be left justified | 3 | 3
NVT-25 / User should be able to select only one radio option | 0 | 0
NVT-3 / Enough space should be provided between field labels | 0 | 0
NVT-4 / Scroll bar should be enabled only when necessary | 4 | 4
NVT-5 / Font size and style should be standard as specified in SRS | 0 | 0
NVT-6 / Description text box should be multi-line | 0 | 0
NVT-7 / Disabled fields should be grayed out | 0 | 0
NVT-8 / Upon click mouse arrow pointer should get changed to cursor | 3 | 2
NVT-9 / User should not be able to type in drop down select lists | 0 | 0
Grand Total | 29 | 27

## Defect per Cycle
Values
Test Cycle | Sum of Execution Defects Count | Sum of Step Defects Count
CWT | 12 | 11
Ad hoc | 4 | 3
Regression | 1 | 2
Sanity | 7 | 6
NVT | 17 | 16
GUI | 13 | 12
Usability | 4 | 4
Grand Total | 29 | 27

## Executions
Key | Project Key | Summary | Title | Priority | Status | Assignee | Reporter | Execution ID | Execution Version | Test Cycle | Execution Status | Execution Defects | Execution Defects Count | Step Defects | Step Defects Count | Executed By | Executed On | Executed On Year | Executed On Month | Executed On Day
CWT-1 | CWT | Test the behavior of required fields | CWT-1 / Test the behavior of required fields | Medium | To Do | David Parker | Katerina Gonzales | 21 | v0.1 | Sanity | PASS |  | 0 |  | 0 | David Parker | 2017-05-02 | 2017 | May | 2
CWT-1 | CWT | Test the behavior of required fields | CWT-1 / Test the behavior of required fields | Medium | To Do | David Parker | Katerina Gonzales | 1 | Unscheduled | Ad hoc | PASS |  | 0 |  | 0 | Matthew Bates | 2017-05-02 | 2017 | May | 2
CWT-2 | CWT | Enter different data types | CWT-2 / Enter different data types | Medium | To Do | Quentin Ortiz | Matthew Bates | 35 | v0.1 | Regression | FAIL | CWT-22 | 1 | CWT-22, CWT-89 | 2 | Katerina Gonzales | 2017-05-02 | 2017 | May | 2
CWT-2 | CWT | Enter different data types | CWT-2 / Enter different data types | Medium | To Do | Quentin Ortiz | Katerina Gonzales | 2 | v0.1 | Ad hoc | UNEXECUTED |  | 0 |  | 0 | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted)
CWT-3 | CWT | Use various field widths | CWT-3 / Use various field widths | Medium | In progress | Quentin Ortiz | Katerina Gonzales | 34 | v0.1 | Regression | WIP |  | 0 |  | 0 | Quentin Ortiz | 2017-05-07 | 2017 | May | 7
CWT-3 | CWT | Use various field widths | CWT-3 / Use various field widths | Medium | To Do | Quentin Ortiz | Matthew Bates | 3 | v1.0 | Sanity | FAIL | CWT-76, CWT-77, CWT78 | 3 | CWT-76, CWT-77 | 2 | Matthew Bates | 2017-05-07 | 2017 | May | 7
CWT-4 | CWT | Onscreen instructions | CWT-4 / Onscreen instructions | Medium | To Do | David Parker | Katerina Gonzales | 20 | v0.1 | Sanity | BLOCKED | CWT-77 | 1 | CWT-77 | 1 | David Parker | 2017-05-07 | 2017 | May | 7
CWT-4 | CWT | Onscreen instructions | CWT-4 / Onscreen instructions | Medium | Done | David Parker | Matthew Bates | 4 | Unscheduled | Ad hoc | PASS |  | 0 |  | 0 | Katerina Gonzales | 2017-05-07 | 2017 | May | 7
CWT-5 | CWT | Keep onscreen instructions brief | CWT-5 / Keep onscreen instructions brief | Medium | To Do | David Parker | Katerina Gonzales | 33 | v0.1 | Regression | UNEXECUTED |  | 0 |  | 0 | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted)
CWT-5 | CWT | Keep onscreen instructions brief | CWT-5 / Keep onscreen instructions brief | Medium | In progress | David Parker | Katerina Gonzales | 19 | v0.1 | Sanity | WIP |  | 0 |  | 0 | David Parker | 2017-05-24 | 2017 | May | 24
CWT-5 | CWT | Keep onscreen instructions brief | CWT-5 / Keep onscreen instructions brief | Medium | In progress | David Parker | Matthew Bates | 5 | v0.1 | Ad hoc | WIP |  | 0 |  | 0 | Matthew Bates | 2017-05-24 | 2017 | May | 24
CWT-6 | CWT | Progress bars appearance at different scenarios | CWT-6 / Progress bars appearance at different scenarios | High | To Do | Matthew Bates | Katerina Gonzales | 6 | v0.1 | Ad hoc | BLOCKED | CWT-55 | 1 | CWT-55 | 1 | Matthew Bates | 2017-05-24 | 2017 | May | 24
CWT-7 | CWT | Same document opened multiple times | CWT-7 / Same document opened multiple times | Medium | To Do | Matthew Bates | Katerina Gonzales | 7 | v1.0 | Ad hoc | FAIL | CWT-17 | 1 | CWT-17 | 1 | Katerina Gonzales | 2017-05-24 | 2017 | May | 24
CWT-8 | CWT | Cosmetic inconsistencies | CWT-8 / Cosmetic inconsistencies | Medium | Done | Quentin Ortiz | Matthew Bates | 32 | v0.1 | Regression | PASS |  | 0 |  | 0 | Quentin Ortiz | 2017-05-24 | 2017 | May | 24
CWT-8 | CWT | Cosmetic inconsistencies | CWT-8 / Cosmetic inconsistencies | Medium | To Do | Quentin Ortiz | Katerina Gonzales | 18 | v0.1 | Sanity | FAIL | CWT-20, CWT-21 | 2 | CWT-20, CWT-21 | 2 | David Parker | 2017-05-24 | 2017 | May | 24
CWT-8 | CWT | Cosmetic inconsistencies | CWT-8 / Cosmetic inconsistencies | Medium | Done | Quentin Ortiz | Katerina Gonzales | 8 | v1.0 | Ad hoc | PASS |  | 0 |  | 0 | Matthew Bates | 2017-06-18 | 2017 | Jun | 18
CWT-9 | CWT | Abbreviation inconsistencies | CWT-9 / Abbreviation inconsistencies | Low | Done | Matthew Bates | Katerina Gonzales | 9 | v0.1 | Ad hoc | PASS |  | 0 |  | 0 | Matthew Bates | 2017-06-18 | 2017 | Jun | 18
CWT-10 | CWT | Confirmations on saving forms | CWT-10 / Confirmations on saving forms | Medium | In progress | Matthew Bates | Matthew Bates | 10 | v0.1 | Ad hoc | WIP |  | 0 |  | 0 | Katerina Gonzales | 2017-06-18 | 2017 | Jun | 18
CWT-11 | CWT | Use type ahead feature for form filling | CWT-11 / Use type ahead feature for form filling | Medium | To Do | Unassigned | Matthew Bates | 31 | v0.1 | Regression | FAIL |  | 0 |  | 0 | Quentin Ortiz | 2017-06-25 | 2017 | Jun | 25
CWT-11 | CWT | Use type ahead feature for form filling | CWT-11 / Use type ahead feature for form filling | Medium | To Do | Unassigned | Katerina Gonzales | 11 | v1.0 | Ad hoc | UNEXECUTED |  | 0 |  | 0 | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted)
CWT-12 | CWT | Try table scrolling edge cases | CWT-12 / Try table scrolling edge cases | Medium | Done | Unassigned | Matthew Bates | 30 | v0.1 | Regression | PASS |  | 0 |  | 0 | Quentin Ortiz | 2017-06-27 | 2017 | Jun | 27
CWT-12 | CWT | Try table scrolling edge cases | CWT-12 / Try table scrolling edge cases | Low | To Do | Unassigned | Katerina Gonzales | 12 | Unscheduled | Ad hoc | FAIL | CWT-18, CWT-19 | 2 | CWT-18 | 1 | Matthew Bates | 2017-06-27 | 2017 | Jun | 27
CWT-13 | CWT | Error logging | CWT-13 / Error logging | Highest | Done | David Parker | Katerina Gonzales | 17 | v0.1 | Sanity | PASS |  | 0 |  | 0 | Katerina Gonzales | 2017-06-27 | 2017 | Jun | 27
CWT-13 | CWT | Error logging | CWT-13 / Error logging | High | Done | David Parker | Matthew Bates | 13 | v1.0 | Ad hoc | PASS |  | 0 |  | 0 | Matthew Bates | 2017-06-27 | 2017 | Jun | 27
CWT-14 | CWT | Try all shortcut keys | CWT-14 / Try all shortcut keys | Medium | Done | David Parker | Matthew Bates | 16 | v0.1 | Sanity | PASS |  | 0 |  | 0 | David Parker | 2017-06-27 | 2017 | Jun | 27
CWT-14 | CWT | Try all shortcut keys | CWT-14 / Try all shortcut keys | Low | To Do | David Parker | Matthew Bates | 14 | Unscheduled | Ad hoc | UNEXECUTED |  | 0 |  | 0 | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted)
CWT-15 | CWT | Invalid menu items | CWT-15 / Invalid menu items | Medium | Done | Quentin Ortiz | Katerina Gonzales | 29 | v0.1 | Regression | PASS |  | 0 |  | 0 | Katerina Gonzales | 2017-07-02 | 2017 | Jul | 2
CWT-15 | CWT | Invalid menu items | CWT-15 / Invalid menu items | Medium | To Do | Quentin Ortiz | Katerina Gonzales | 15 | Unscheduled | Ad hoc | FAIL |  | 0 |  | 0 | Quentin Ortiz | 2017-07-03 | 2017 | Jul | 3
CWT-16 | CWT | Keyboard switching for number type fields on mobile | CWT-16 / Keyboard switching for number type fields on mobile | Medium | Done | Matthew Bates | Matthew Bates | 36 | v0.1 | Sanity | PASS |  | 0 |  | 0 | John Hopkins | 2017-07-02 | 2017 | Jul | 2
CWT-23 | CWT | Load website with various connections quality | CWT-23 / Load website with various connections quality | High | To Do | Unassigned | John Hopkins | 37 | v0.3 | Ad hoc | UNEXECUTED |  | 0 |  | 0 | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted)
CWT-24 | CWT | Try different browsers for compatibility | CWT-24 / Try different browsers for compatibility | Medium | Done | Unassigned | John Hopkins | 38 | v1.0 | Ad hoc | PASS |  | 0 |  | 0 | John Hopkins | 2017-07-02 | 2017 | Jul | 2
CWT-26 | CWT | Response times at different connection speeds | CWT-26 / Response times at different connection speeds | Medium | Done | Unassigned | John Hopkins | 39 | Unscheduled | Ad hoc | PASS |  | 0 |  | 0 | John Hopkins | 2017-07-02 | 2017 | Jul | 2
CWT-27 | CWT | Verify required SSL security compliance | CWT-27 / Verify required SSL security compliance | Medium | To Do | John Hopkins | John Hopkins | 40 | v0.1 | Sanity | FAIL | CWT-99 | 1 | CWT-99 | 1 | John Hopkins | 2017-07-02 | 2017 | Jul | 2
CWT-28 | CWT | Database consistency | CWT-28 / Database consistency | Medium | To Do | Unassigned | John Hopkins | 42 | Unscheduled | Ad hoc | FAIL |  | 0 |  | 0 | Quentin Ortiz | 2017-07-02 | 2017 | Jul | 2
CWT-29 | CWT | HTTP protocol used to maintain website cookies | CWT-29 / HTTP protocol used to maintain website cookies | Low | Done | Unassigned | John Hopkins | 41 | Unscheduled | Ad hoc | PASS |  | 0 |  | 0 | Katerina Gonzales | 2017-08-02 | 2017 | Aug | 2
NVT-1 | NVT | All fields on page should be aligned properly | NVT-1 / All fields on page should be aligned properly | Medium | Done | David Parker | Katerina Gonzales | 21 | v0.3 | GUI | PASS |  | 0 |  | 0 | David Parker | 2017-08-03 | 2017 | Aug | 3
NVT-2 | NVT | Numeric values should be right justified | NVT-2 / Numeric values should be right justified | Medium | Done | David Parker | Katerina Gonzales | 1 | v0.2 | Usability | PASS |  | 0 |  | 0 | Matthew Bates | 2017-08-04 | 2017 | Aug | 4
NVT-2 | NVT | Numeric values should be right justified | NVT-2 / Numeric values should be right justified | Medium | To Do | Quentin Ortiz | Matthew Bates | 35 | v0.2 | GUI | FAIL | NVT-26, NVT-27 | 2 | NVT-26, NVT-27 | 2 | Katerina Gonzales | 2017-08-04 | 2017 | Aug | 4
NVT-2 | NVT | Numeric values should be right justified | NVT-2 / Numeric values should be right justified | Medium | To Do | Quentin Ortiz | Katerina Gonzales | 2 | v0.2 | GUI | UNEXECUTED |  | 0 |  | 0 | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted)
NVT-3 | NVT | Enough space should be provided between field labels | NVT-3 / Enough space should be provided between field labels | Low | In progress | Quentin Ortiz | Katerina Gonzales | 34 | Unscheduled | Usability | WIP |  | 0 |  | 0 | Quentin Ortiz | 2017-08-04 | 2017 | Aug | 4
NVT-4 | NVT | Scroll bar should be enabled only when necessary | NVT-4 / Scroll bar should be enabled only when necessary | Highest | To Do | Quentin Ortiz | Matthew Bates | 3 | v0.1 | Usability | FAIL | NVT-26, NVT-27, NVT-28, NVT-29 | 4 | NVT-26, NVT-27, NVT-28, NVT-29 | 4 | Matthew Bates | 2017-08-04 | 2017 | Aug | 4
NVT-5 | NVT | Font size and style should be standard as specified in SRS | NVT-5 / Font size and style should be standard as specified in SRS | High | To Do | David Parker | Katerina Gonzales | 20 | v0.1 | GUI | BLOCKED |  | 0 |  | 0 | Katerina Gonzales | 2017-08-14 | 2017 | Aug | 14
NVT-5 | NVT | Font size and style should be standard as specified in SRS | NVT-5 / Font size and style should be standard as specified in SRS | Medium | Done | David Parker | Matthew Bates | 4 | Unscheduled | Usability | PASS |  | 0 |  | 0 | Matthew Bates | 2017-08-14 | 2017 | Aug | 14
NVT-5 | NVT | Font size and style should be standard as specified in SRS | NVT-5 / Font size and style should be standard as specified in SRS | Low | To Do | David Parker | Katerina Gonzales | 33 | Unscheduled | Usability | FAIL |  | 0 |  | 0 | Quentin Ortiz | 2017-08-14 | 2017 | Aug | 14
NVT-5 | NVT | Font size and style should be standard as specified in SRS | NVT-5 / Font size and style should be standard as specified in SRS | Medium | In progress | David Parker | Katerina Gonzales | 19 | Unscheduled | GUI | WIP |  | 0 |  | 0 | David Parker | 2017-08-14 | 2017 | Aug | 14
NVT-6 | NVT | Description text box should be multi-line | NVT-6 / Description text box should be multi-line | Medium | In progress | David Parker | Matthew Bates | 5 | v0.3 | Usability | WIP |  | 0 |  | 0 | Katerina Gonzales | 2017-08-14 | 2017 | Aug | 14
NVT-7 | NVT | Disabled fields should be grayed out | NVT-7 / Disabled fields should be grayed out | High | To Do | Matthew Bates | Katerina Gonzales | 6 | Unscheduled | GUI | BLOCKED |  | 0 |  | 0 | Matthew Bates | 2017-08-17 | 2017 | Aug | 17
NVT-8 | NVT | Upon click mouse arrow pointer should get changed to cursor | NVT-8 / Upon click mouse arrow pointer should get changed to cursor | Medium | To Do | Matthew Bates | Katerina Gonzales | 7 | v0.1 | GUI | FAIL | NVT-26, NVT-28, NVT-29 | 3 | NVT-26, NVT-28 | 2 | Matthew Bates | 2017-08-17 | 2017 | Aug | 17
NVT-9 | NVT | User should not be able to type in drop down select lists | NVT-9 / User should not be able to type in drop down select lists | Medium | Done | Quentin Ortiz | Matthew Bates | 32 | Unscheduled | Usability | PASS |  | 0 |  | 0 | Quentin Ortiz | 2017-08-17 | 2017 | Aug | 17
NVT-10 | NVT | Information filled by users should remain intact when there is error message on page submit | NVT-10 / Information filled by users should remain intact when there is error message on page submit | Medium | To Do | Quentin Ortiz | Katerina Gonzales | 18 | v0.1 | GUI | FAIL | NVT-26, NVT-28 | 2 | NVT-26, NVT-28 | 2 | Katerina Gonzales | 2017-08-19 | 2017 | Aug | 19
NVT-11 | NVT | Check if proper field labels are used in error messages | NVT-11 / Check if proper field labels are used in error messages | Medium | Done | Quentin Ortiz | Katerina Gonzales | 8 | Unscheduled | Usability | PASS |  | 0 |  | 0 | Matthew Bates | 2017-08-19 | 2017 | Aug | 19
NVT-12 | NVT | Dropdown field values should be displayed in defined sort order | NVT-12 / Dropdown field values should be displayed in defined sort order | Low | Done | Matthew Bates | Katerina Gonzales | 9 | v0.1 | GUI | PASS |  | 0 |  | 0 | Matthew Bates | 2017-08-19 | 2017 | Aug | 19
NVT-12 | NVT | Dropdown field values should be displayed in defined sort order | NVT-12 / Dropdown field values should be displayed in defined sort order | Medium | In progress | Matthew Bates | Matthew Bates | 10 | v0.3 | Usability | WIP |  | 0 |  | 0 | Matthew Bates | 2017-08-20 | 2017 | Aug | 20
NVT-12 | NVT | Dropdown field values should be displayed in defined sort order | NVT-12 / Dropdown field values should be displayed in defined sort order | Medium | To Do | Unassigned | Matthew Bates | 31 | v0.1 | GUI | UNEXECUTED |  | 0 |  | 0 | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted)
NVT-13 | NVT | Tab and Shift+Tab order should work properly | NVT-13 / Tab and Shift+Tab order should work properly | Medium | To Do | Unassigned | Katerina Gonzales | 11 | Unscheduled | Usability | FAIL |  | 0 |  | 0 | Quentin Ortiz | 2017-08-20 | 2017 | Aug | 20
NVT-14 | NVT | Default radio options should be pre-selected on page load | NVT-14 / Default radio options should be pre-selected on page load | Medium | Done | Unassigned | Matthew Bates | 30 | v0.1 | GUI | PASS |  | 0 |  | 0 | Quentin Ortiz | 2017-08-20 | 2017 | Aug | 20
NVT-15 | NVT | Field specific help messages should be available | NVT-15 / Field specific help messages should be available | Low | To Do | Unassigned | Katerina Gonzales | 12 | v0.3 | GUI | FAIL | NVT-26, NVT-28 | 2 | NVT-26, NVT-28 | 2 | Matthew Bates | 2017-08-20 | 2017 | Aug | 20
NVT-15 | NVT | Field specific help messages should be available | NVT-15 / Field specific help messages should be available | Highest | To Do | David Parker | Katerina Gonzales | 17 | v1.0 | GUI | BLOCKED |  | 0 |  | 0 | Quentin Ortiz | 2017-08-20 | 2017 | Aug | 20
NVT-15 | NVT | Field specific help messages should be available | NVT-15 / Field specific help messages should be available | High | Done | David Parker | Matthew Bates | 13 | Unscheduled | Usability | PASS |  | 0 |  | 0 | Matthew Bates | 2017-08-20 | 2017 | Aug | 20
NVT-16 | NVT | Check if correct fields are highlighted in case of errors | NVT-16 / Check if correct fields are highlighted in case of errors | Medium | Done | David Parker | Matthew Bates | 16 | v0.3 | GUI | PASS |  | 0 |  | 0 | David Parker | 2017-09-12 | 2017 | Sep | 12
NVT-17 | NVT | Check if dropdown list options are readable | NVT-17 / Check if dropdown list options are readable | Low | To Do | David Parker | Matthew Bates | 14 | Unscheduled | Usability | UNEXECUTED |  | 0 |  | 0 | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted)
NVT-17 | NVT | Check if dropdown list options are readable | NVT-17 / Check if dropdown list options are readable | Medium | Done | Quentin Ortiz | Katerina Gonzales | 29 | Unscheduled | GUI | PASS |  | 0 |  | 0 | Katerina Gonzales | 2017-09-12 | 2017 | Sep | 12
NVT-17 | NVT | Check if dropdown list options are readable | NVT-17 / Check if dropdown list options are readable | Medium | To Do | Quentin Ortiz | Katerina Gonzales | 15 | v0.2 | Usability | FAIL |  | 0 |  | 0 | Quentin Ortiz | 2017-09-12 | 2017 | Sep | 12
NVT-18 | NVT | All buttons on page should be accessible by keyboard shortcuts | NVT-18 / All buttons on page should be accessible by keyboard shortcut | High | Done | Matthew Bates | Matthew Bates | 36 | v0.2 | GUI | PASS |  | 0 |  | 0 | John Hopkins | 2017-09-12 | 2017 | Sep | 12
NVT-19 | NVT | Check all pages for broken images | NVT-19 / Check all pages for broken images | Medium | To Do | Unassigned | John Hopkins | 37 | v0.3 | GUI | FAIL |  | 0 |  | 0 | Katerina Gonzales | 2017-09-19 | 2017 | Sep | 19
NVT-19 | NVT | Check all pages for broken images | NVT-19 / Check all pages for broken images | Medium | Done | Unassigned | John Hopkins | 38 | v0.2 | Usability | PASS |  | 0 |  | 0 | John Hopkins | 2017-09-19 | 2017 | Sep | 19
NVT-20 | NVT | Check all pages for broken links | NVT-20 / Check all pages for broken links | Medium | Done | Unassigned | John Hopkins | 39 | v0.2 | GUI | PASS |  | 0 |  | 0 | Katerina Gonzales | 2017-09-19 | 2017 | Sep | 19
NVT-20 | NVT | Check all pages for broken links | NVT-20 / Check all pages for broken links | Medium | To Do | John Hopkins | John Hopkins | 40 | v0.2 | GUI | FAIL | NVT-26 | 1 | NVT-26 | 1 | John Hopkins | 2017-09-19 | 2017 | Sep | 19
NVT-21 | NVT | All pages should have title | NVT-21 / All pages should have title | Low | To Do | Unassigned | John Hopkins | 42 | v0.3 | Usability | UNEXECUTED |  | 0 |  | 0 | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted)
NVT-22 | NVT | Confirmation messages should be displayed before performing any update or delete operation | NVT-22 / Confirmation messages should be displayed before performing any update or delete operation | Medium | Done | Unassigned | John Hopkins | 41 | v0.2 | GUI | PASS |  | 0 |  | 0 | John Hopkins | 2017-09-19 | 2017 | Sep | 19
NVT-22 | NVT | Confirmation messages should be displayed before performing any update or delete operation | NVT-22 / Confirmation messages should be displayed before performing any update or delete operation | Medium | Done | Quentin Ortiz | Katerina Gonzales | 30 | v0.2 | GUI | PASS |  | 0 |  | 0 | Katerina Gonzales | 2017-10-10 | 2017 | Oct | 10
NVT-23 | NVT | Hour glass should be displayed when application is busy | NVT-23 / Hour glass should be displayed when application is busy | Medium | Done | Matthew Bates | Matthew Bates | 12 | v0.2 | Usability | PASS |  | 0 |  | 0 | John Hopkins | 2017-10-10 | 2017 | Oct | 10
NVT-24 | NVT | Page text should be left justified | NVT-24 / Page text should be left justified | Medium | To Do | Quentin Ortiz | John Hopkins | 17 | v0.3 | GUI | FAIL | NVT-26, NVT-28, NVT-29 | 3 | NVT-26, NVT-28, NVT-29 | 3 | Quentin Ortiz | 2017-10-10 | 2017 | Oct | 10
NVT-25 | NVT | User should be able to select only one radio option | NVT-25 / User should be able to select only one radio option | Low | To Do | Matthew Bates | John Hopkins | 13 | v0.2 | GUI | UNEXECUTED |  | 0 |  | 0 | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted) | (Unexecuted)